## Options Comparison
Team Connect → iManage Migration — Staging Environment Options
Additional technology work, effort and timelines for the ETL migration and its staging database
Dimension | Option 1 — Data Factory in the initial PID | Option 2 — Data Factory added later | Option 3 — VMCE2 SQL Server staging | Comment
Added environment setup (elapsed) | 2 – 4 weeks | 8 – 13 weeks | 7 – 11 weeks | Option 1 rides the PID and ARE deployment already in flight
ETL build, test and wave execution | 16 – 22 weeks | 16 – 22 weeks | 20 – 28 weeks | Option 3 adds 4–6 weeks for hand-built orchestration
Total added project time | 18 – 26 weeks (≈ 4 – 6 months) | 24 – 36 weeks (≈ 5.5 – 8 months) | 26 – 38 weeks (≈ 6 – 9 months) | Critical-path elapsed time, not person-effort
Delta versus Option 1 | Baseline | +6 to +10 weeks | +8 to +12 weeks | The Option 2 delta is entirely rework
New infrastructure requests | Integration runtime and firewall only | Full PID, review, CIDR, firewall and ARE cycle again | Server request, VM, SQL install, AD, firewall, DBA — per environment | Each request carries its own queue and SLA
Second security review needed | No — covered by the platform CSP review | Yes — delta CSP and privacy review | Yes — plus server hardening and vulnerability remediation | Security review is the highest-variance gate
Orchestration, retry, logging, lineage | Native to Data Factory | Native to Data Factory | Hand-built and TD-maintained | The largest hidden cost in Option 3
Connectors to Team Connect sources | Managed connectors for SQL, Oracle and blob | Managed connectors for SQL, Oracle and blob | Custom extraction per source | Team Connect spans on-prem SQL, cloud Oracle and blob
Risk to the live integration platform | None — deployed together | Regression pass needed after the landing zone changes | Low — separate estate | Option 2 modifies a platform already in production
Ongoing run cost | Low — PaaS, no OS or licence ownership | Low — same end state as Option 1 | High — OS patching, SQL licensing, backup, DR testing | Option 3's cost does not end
Reuse for future data workloads | High — platform capability from day one | High — same capability, later | Low — single-purpose server | Future integrations and reporting can reuse Data Factory
Verdict | RECOMMENDED — decide before the PID is baselined | AVOID — the entire delta is avoidable rework | NOT RECOMMENDED unless policy blocks PaaS | Same end state for Options 1 and 2
KEY FINDINGS
1. The migration needs a staging layer regardless. Team Connect data has to be extracted, transformed into an iManage-oriented
model, validated and loaded in waves.
2. Option 1 is close to free. If Data Factory, ADLS/Blob and Azure SQL staging are named in the PID the Infrastructure Architect is
already producing for the integration platform, they are provisioned in the same ARE deployment. The only genuinely new work
is the self-hosted integration runtime for on-premises Team Connect connectivity, and the firewall rules to it.
3. Option 2 reaches exactly the same end state as Option 1, but pays for PID rework, a delta security review, new subnet allocation,
an ARE redeployment and a regression pass over the already-live integration platform.
4. Option 3 is slower per environment (PAT 5-day SLA, PROD 10-day SLA, plus VM build, SQL install, AD groups, firewall and DBA
setup) and has no orchestration engine, so extraction, scheduling, retry, logging and lineage are written and maintained by TD.
5. The decision is about timing, not technology. Naming Data Factory and the staging database in the PID costs about a week of
design effort now. Adding them in three months costs two to three months.
ACTION
Confirm with the Infrastructure Architect that Azure Data Factory, ADLS Gen2 / Blob Storage and the Azure SQL staging database
are in scope of the PID being produced for the iManage integration platform, before that PID goes to architecture review.
That single action is the difference between Option 1 and Option 2.
ASSUMPTIONS AND RISKS
The integration platform PID has not yet been baselined — if it has, Option 1 is gone and the migration defaults to Option 2.
iManage supports a bulk or API-based load at the required volume — confirm ingestion limits and throttling with Kroll.
Migration runs in waves rather than a single cutover, so wave 1 can go live while later waves are still being transformed.
Team Connect data quality is as expected — worse quality grows cleansing scope, mock migration cycles and UAT.
Migration and integration are not competing for the same TD developers.
On-premises Team Connect sources are reachable from Azure through a self-hosted integration runtime.

## Steps by Option
Migration Work Steps by Option
Environment steps differ by option. The ETL build, test and wave execution steps at the bottom apply to all three.
ID | Step | What It Involves | Accountable Team | SLA / Duration | Elapsed Low (wks) | Elapsed High (wks) | Dependency / Note
OPTION 1 — DATA FACTORY AND AZURE SQL STAGING INCLUDED IN THE INITIAL PID · 2–4 weeks added · RECOMMENDED
1.1 | Name Data Factory, ADLS/Blob and Azure SQL staging in the PID | Add the migration data services to the platform infrastructure design the IA is already producing | Infra Architect + TD | 0.5 – 1 week | 0.5 | 1 | Must happen before the PID goes to architecture review
1.2 | Data classification and privacy assessment for migration data | Matter data classification, retention and residency handled inside the same Cloud CSP review | Privacy + Security | Within CSP review | 0 | 1 | No separate review cycle if included up front
1.3 | Data subnet / CIDR allocation | Covered by the per-environment allocation already requested for the platform | Network | 3 days per env | 0 | 0.6 | No additional request if scoped in the PID
1.4 | Self-hosted integration runtime for on-premises sources | VM build plus runtime installation so Data Factory can reach on-prem Team Connect SQL and Oracle | TD Infrastructure | 1 – 2 weeks | 1 | 2 | The only genuinely new infrastructure component
1.5 | Firewall rules to Team Connect sources | Paths from the integration runtime to on-prem SQL, cloud Oracle and blob storage | Network | 5 business day SLA | 1 | 1.5 | Per environment
1.6 | ARE deploys Data Factory, ADLS and Azure SQL staging | Provisioned in the same ARE deployment as the integration platform resources | ARE | Within platform deploy | 0 | 0.5 | No separate change ticket cycle
1.7 | DBA engagement for the Azure SQL staging database | Sizing, backup and retention policy, purge strategy, access model and monitoring | DBA | 1 week | 1 | 1.5 | Parallel to the ARE deployment
OPTION 2 — DATA FACTORY ADDED AFTER THE PID IS BASELINED · 8–13 weeks added · +6 to +10 weeks of rework versus Option 1
2.1 | Re-engage the Infrastructure Architect and update the PID | Reopen the baselined design, add the data services and re-issue for approval | Infra Architect | 2 weeks | 2 | 2.5 | Serial — nothing downstream starts until re-approved
2.2 | Delta architecture review | Architecture governance review of the amended design | TD Architecture | 1 – 2 weeks | 1 | 2 | 2.1
2.3 | Delta Cloud CSP and privacy review | New data flows, classification and egress paths reviewed again | Security / Network / Privacy | 1 – 3 weeks | 1 | 3 | Highest-variance step
2.4 | New CIDR / subnet allocation per environment | Fresh network address requests for the data subnet in each environment | Network | 3 – 5 days per env | 1 | 2 | 2.2
2.5 | Firewall requests for source connectivity | Rules from the new subnet to on-prem SQL, cloud Oracle and blob storage | Network | 5 business day SLA | 1 | 1.5 | 2.4
2.6 | ARE redeploy of the database and Data Factory | Add the new resources into the existing landing zone through the ARE pipeline | ARE | 2 – 3 weeks | 2 | 3 | 2.4, 2.5
2.7 | ARE deployment and promotion through PAT and PROD | Environment-by-environment deployment with change tickets and verification | ARE | 2 – 3 weeks | 2 | 3 | 2.6
2.8 | Self-hosted integration runtime and DBA setup | The same work as Option 1 steps 1.4 and 1.7, executed later | TD Infrastructure + DBA | 1 – 2 weeks | 1 | 2 | 2.7
2.9 | Regression of the live integration platform | Confirm the operational integration still works after the landing zone is modified | TD QA | 1 – 2 weeks | 1 | 2 | 2.7 — not required in Option 1
OPTION 3 — VMCE2 SQL SERVER STAGING DATABASE (IaaS) · 7–11 weeks added plus 4–6 weeks of extra development
3.1 | Submit VMCE2 server request — PAT | Server build request raised for the PAT environment | TD Infrastructure | 5 business day SLA | 1 | 1.5 | Approved project and cost centre
3.2 | Submit VMCE2 server request — PROD | Server build request raised for production | TD Infrastructure | 10 business day SLA | 2 | 2.5 | Longer SLA than PAT — raise both together
3.3 | VM provisioning and build | Virtual machine built and released to the requesting team | TD Infrastructure | 3 – 5 days per env | 1 | 1.5 | 3.1, 3.2
3.4 | IP assignment, storage allocation and SQL Server installation | Network address, data and log volume sizing, SQL install and instance configuration | TD Infrastructure + DBA | 5 days per env | 1 | 2 | 3.3
3.5 | AD group provisioning for server and database access | Groups for administrators, developers and service accounts across each environment | IAM | 3 – 5 days | 1 | 1.5 | 3.4
3.6 | Firewall requests | Paths from the staging server to Team Connect sources and out to iManage | Network | 5 business day SLA | 1 | 1.5 | 3.4 — per environment
3.7 | DBA setup and standards onboarding | Databases, logins, schemas, backup schedule, HA/DR, monitoring agents and patch windows | DBA | 1 – 2 weeks | 1 | 2 | 3.4, 3.5
3.8 | Server hardening, vulnerability scan and remediation | Baseline hardening, scanning and security sign-off before data lands | Security + Infrastructure | 1 – 2 weeks | 1 | 2 | 3.4
3.9 | Build the extraction layer by hand | SSIS packages or custom code per Team Connect source, with no managed connectors | TD Dev | +2 – 3 weeks | 2 | 3 | Native to Data Factory in Options 1 and 2
3.10 | Build scheduling, retry, logging and lineage | Job scheduler, failure handling, restartability, run history and audit logging | TD Dev | +2 – 3 weeks | 2 | 3 | Native to Data Factory in Options 1 and 2
3.11 | Steady-state server ownership | OS patching, SQL licensing and upgrades, capacity, backup verification and DR testing | TD Infrastructure + DBA | Ongoing | — | — | No equivalent obligation on the PaaS options
ETL BUILD, TEST AND WAVE EXECUTION · common to all three options · 16–22 weeks (Options 1 and 2) or 20–28 weeks (Option 3)
M1 | Team Connect source discovery and data profiling | Identify every source — on-prem SQL, cloud Oracle, blob — with record counts, volumes and data quality | TD Data + TC SMEs | 15 person-days | 2 | 3 | Source system access
M2 | Matter data mapping: Team Connect to iManage | Field-level mapping into an iManage-oriented staging model, including reference and code values | TD Data + Kroll | 20 person-days | 3 | 4 | M1
M3 | Data quality assessment and cleansing rules | Profile defects, define cleansing rules, agree what is migrated, archived or dropped | TD Data + business | 10 person-days | 2 | 3 | M1
M4 | Staging model and migration control table design | Azure SQL as an iManage-oriented staging model, plus batch and record-level control tables | TD Data Architecture | 18 person-days | 2 | 3 | M2
M5 | Extraction pipelines per source | Ingestion into the RAW layer, with an immutable raw copy retained for replay | TD Dev | 15 person-days | 2 | 3 | M1, environment ready
M6 | Transformation and curation | RAW to CURATED to READY layering, cleansing rules and canonical shaping | TD Dev | 20 person-days | 3 | 4 | M2, M3, M5
M7 | Validation, reconciliation and exception reporting | Row counts, referential integrity, mandatory fields, business rules and an exception queue | TD Dev + QA | 15 person-days | 2 | 3 | M6
M8 | Load into iManage | Load the READY layer via API or bulk import, with per-record status capture and error handling | TD Dev + Kroll | 15 person-days | 2 | 3 | M6
M9 | Wave orchestration and scheduling | Wave definition, batching, sequencing, restartability and operational scheduling | TD Dev | 8 person-days | 1 | 2 | M4, M8
M10 | Mock migration cycles 1 and 2 | Two full dry runs with reconciliation, defect remediation and formal sign-off | TD QA + Dev | 20 person-days | 4 | 5 | M7, M8
M11 | Business data validation and UAT | Legal operations validate migrated matters in iManage against Team Connect records | Business + TD | 15 person-days | 2 | 3 | M10
M12 | Production wave execution | Execute wave by wave with reconciliation after each — roughly 1–2 weeks per wave | TD Dev + business | 5 pd per wave | 1 | 2 | M11 — per wave
M13 | Post-migration reconciliation and defect remediation | Re-run failed records, close exception queues, produce the final reconciliation evidence pack | TD Dev + business | 10 person-days | 2 | 3 | M12
M14 | Decommission staging and archive the raw layer | Retire the staging database, archive the raw copy per retention policy, release infrastructure | TD Infrastructure + DBA | 3 person-days | 1 | 1 | M13
| TOTAL ADDED PROJECT TIME — Option 1 (Data Factory in the initial PID) |  |  |  | 18 wks | 26 wks | ≈ 4 – 6 months
| TOTAL ADDED PROJECT TIME — Option 2 (Data Factory added later) |  |  |  | 24 wks | 36 wks | ≈ 5.5 – 8 months
| TOTAL ADDED PROJECT TIME — Option 3 (VMCE2 SQL Server staging) |  |  |  | 26 wks | 38 wks | ≈ 6 – 9 months
NOTE
Environment steps and the ETL build run partly in parallel, so option totals are less than the sum of the rows above.
Wave execution repeats per wave, so the total depends on how many waves are agreed with the business.