## 1. Summary
Team Connect → iManage Matter Data Migration ¦ Staging Environment Options
Additional technology work effort, steps and timelines for the ETL migration and its staging database
Option | Added environment setup (elapsed) | ETL build, test & waves | Total added elapsed time | Run / ownership cost | Fit for purpose | Verdict
Option 1 — ADF + Azure SQL staging included in the INITIAL PID | 2 – 4 weeks | 16 – 22 weeks | 18 – 26 weeks (≈ 4 – 6 months) | Low — PaaS, no OS or SQL licence ownership | Purpose-built for ETL: connectors, orchestration, wave control, lineage | RECOMMENDED — decide before the PID is baselined
Option 2 — ADF added AFTER the PID is baselined | 8 – 13 weeks | 16 – 22 weeks | 24 – 36 weeks (≈ 5.5 – 8 months) | Low — same end state as Option 1 | Identical end state to Option 1, reached 6 – 10 weeks later | AVOID — the entire delta is avoidable rework
Option 3 — VMCE2 SQL Server staging database (IaaS) | 7 – 11 weeks | 20 – 28 weeks | 26 – 38 weeks (≈ 6 – 9 months) | High — TD owns the OS, patching, SQL licensing, backup and DR | No native orchestration — extract, scheduling, retry and lineage all hand-built | NOT RECOMMENDED unless a policy constraint blocks PaaS
KEY FINDINGS
1. The migration needs a staging layer regardless. Team Connect data cannot be pushed straight into iManage — it has to be
extracted, transformed into an iManage-oriented model, validated, and then loaded in waves.
2. Option 1 is close to free. If ADF, ADLS/Blob and Azure SQL staging are named in the PID that the Infrastructure Architect is
already producing for the integration platform, they are provisioned in the same ARE deployment. The only genuinely
additional work is the self-hosted integration runtime for on-premises Team Connect connectivity and the firewall rules to it.
3. Option 2 buys nothing. It reaches exactly the same end state as Option 1 but pays 6 – 10 extra weeks for PID rework, a delta
security review, new subnet allocation, an ARE redeployment and a regression pass over the already-live integration platform.
4. Option 3 is the most expensive on both axes. It is slower to stand up per environment (PAT 5-day SLA, PROD 10-day SLA, plus
VM build, SQL install, AD groups, firewall and DBA setup) and it has no orchestration engine, so extraction, scheduling, retry,
logging, lineage and wave control all have to be written and maintained by TD. It also creates a permanent run-cost tail.
5. The single decision that matters is timing, not technology. Naming ADF and the staging database in the PID today costs
roughly one week of design effort. Adding them in three months costs two to three months.
IMMEDIATE ACTION
Confirm with the Infrastructure Architect that Azure Data Factory, ADLS Gen2 / Blob Storage and the Azure SQL staging database
are in scope of the PID being produced for the iManage integration platform — before that PID goes to architecture review.
That one action is the difference between Option 1 and Option 2.

## 2. Option 1 (ADF in PID)
Option 1 — Azure Data Factory + Azure SQL staging included in the INITIAL PID
The migration data services are provisioned alongside the integration platform. No second infrastructure cycle. RECOMMENDED.
ID | Step | What It Involves | Accountable Team | SLA / Duration | Elapsed Low (wks) | Elapsed High (wks) | Dependency / Note
ADDITIONAL ENVIRONMENT SETUP — most of it is absorbed by the platform PID and the ARE deployment already in flight
1.1 | Name ADF, ADLS/Blob and Azure SQL staging in the PID | Add the migration data services to the same platform infrastructure design the IA is already producing | Infra Architect + TD | 0.5 – 1 week | 0.5 | 1 | Must happen BEFORE the PID goes to architecture review
1.2 | Data classification and privacy assessment for migration data | Matter data classification, retention and residency handled inside the same Cloud CSP review, not a second one | Privacy + Security | Within CSP review | 0 | 1 | No separate review cycle if included up front
1.3 | Data subnet / CIDR allocation | Covered by the same per-environment allocation already requested for the platform | Network | 3 days per env | 0 | 0.6 | No additional request if scoped in the PID
1.4 | Self-hosted integration runtime for on-premises sources | VM build plus IR installation and registration so ADF can reach on-prem Team Connect SQL and Oracle | TD Infrastructure | 1 – 2 weeks | 1 | 2 | Genuinely additional — the only new infrastructure component
1.5 | Firewall rules to Team Connect sources | Paths from the integration runtime to on-prem SQL, cloud Oracle and blob storage | Network | 5 business day SLA | 1 | 1.5 | Per environment
1.6 | ARE deploys ADF, ADLS and Azure SQL staging | Provisioned in the same ARE deployment as the integration platform resources | ARE | Within platform deploy | 0 | 0.5 | No separate change ticket cycle
1.7 | DBA engagement for the Azure SQL staging database | Sizing, backup and retention policy, purge strategy, access model and monitoring | DBA | 1 week | 1 | 1.5 | Runs parallel to the ARE deployment
SUBTOTAL — ADDITIONAL ENVIRONMENT SETUP: 2 – 4 weeks elapsed, largely in parallel with the platform runway
| TOTAL ADDED ENVIRONMENT SETUP |  |  |  | 2 wks | 4 wks | Mostly parallel to the platform runway
| PLUS ETL BUILD, TEST AND WAVE EXECUTION (see sheet 5) |  |  |  | 16 wks | 22 wks | Common to all three options
| TOTAL ADDED PROJECT TIME |  |  |  | 18 wks | 26 wks | ≈ 4 – 6 months
WHY THIS IS THE CHEAPEST PATH
The whole advantage of this option is timing, not technology — it is the same target state as Option 2, requested earlier.
Everything from step 1.1 through 1.6 rides on infrastructure requests that are already being raised for the integration platform.
The window closes when the PID goes to architecture review. After that, this becomes Option 2 and costs 6 – 10 additional weeks.

## 3. Option 2 (ADF added later)
Option 2 — Azure Data Factory added AFTER the PID has been baselined
Same end state as Option 1, reached 6 to 10 weeks later. Every step on this sheet is avoidable rework.
ID | Step | What It Involves | Accountable Team | SLA / Duration | Elapsed Low (wks) | Elapsed High (wks) | Dependency / Note
REWORK CYCLE — the platform PID is already baselined, so the design, review and deployment loop has to be reopened
2.1 | Re-engage the Infrastructure Architect and update the PID | Reopen the baselined design, add the ADF, storage and Azure SQL staging components, re-issue for approval | Infra Architect | 2 weeks | 2 | 2.5 | Serial — nothing downstream can start until the PID is re-approved
2.2 | Delta architecture review | Architecture governance review of the amended design | TD Architecture | 1 – 2 weeks | 1 | 2 | 2.1
2.3 | Delta Cloud CSP / privacy review | New data flows, new data classification, new egress paths and control mapping re-reviewed | Security / Network / Privacy | 1 – 3 weeks | 1 | 3 | Highest-variance step — findings restart the loop
2.4 | New CIDR / subnet allocation per environment | Fresh network address requests for the data subnet in each environment | Network | 3 – 5 days per env | 1 | 2 | 2.2 — repeated for DEV, PAT and PROD
2.5 | Firewall requests for Team Connect source connectivity | Rules from the new subnet to on-prem SQL, cloud Oracle and blob storage | Network | 5 business day SLA | 1 | 1.5 | 2.4
2.6 | ARE redeploy of the database and Data Factory | Add the new resources into the existing landing zone through the ARE pipeline | ARE | 2 – 3 weeks | 2 | 3 | 2.4, 2.5
2.7 | ARE deployment and promotion through PAT and PROD | Environment-by-environment deployment with change tickets and verification | ARE | 2 – 3 weeks | 2 | 3 | 2.6
2.8 | Self-hosted integration runtime and DBA setup | Same work as Option 1 steps 1.4 and 1.7, just executed later | TD Infrastructure + DBA | 1 – 2 weeks | 1 | 2 | 2.7
2.9 | Regression of the live integration platform after redeployment | Confirm the operational integration still functions after the landing zone is modified | TD QA | 1 – 2 weeks | 1 | 2 | 2.7 — not required in Option 1
SUBTOTAL — ADDITIONAL ENVIRONMENT SETUP: 8 – 13 weeks elapsed, largely serial
| TOTAL ADDED ENVIRONMENT SETUP |  |  |  | 8 wks | 13 wks | Largely serial — limited parallelism available
| PLUS ETL BUILD, TEST AND WAVE EXECUTION (see sheet 5) |  |  |  | 16 wks | 22 wks | Common to all three options
| TOTAL ADDED PROJECT TIME |  |  |  | 24 wks | 36 wks | ≈ 5.5 – 8 months
| COST OF NOT DECIDING NOW (Option 2 minus Option 1) |  |  |  | +6 wks | +10 wks | Pure rework — no functional benefit
WHAT THIS OPTION BUYS — NOTHING
Nothing on this sheet delivers a capability that Option 1 does not also deliver.
The delta is entirely the cost of reopening a baselined design: a second architecture review, a second security review,
a second network allocation cycle, an ARE redeployment, and a regression pass over a platform that is already in production.
If the PID has not yet gone to architecture review, this option is still avoidable today.

## 4. Option 3 (VMCE2 SQL)
Option 3 — VMCE2 SQL Server staging database (infrastructure-as-a-service)
Slower to stand up per environment, more code to write because there is no orchestration engine, and a permanent run-cost tail.
ID | Step | What It Involves | Accountable Team | SLA / Duration | Elapsed Low (wks) | Elapsed High (wks) | Dependency / Note
SERVER PROVISIONING — repeated for every environment
3.1 | Submit VMCE2 server request — PAT | Server build request raised against the project for the PAT environment | TD Infrastructure | 5 business day SLA | 1 | 1.5 | Approved project and cost centre
3.2 | Submit VMCE2 server request — PROD | Server build request raised for the production environment | TD Infrastructure | 10 business day SLA | 2 | 2.5 | Longer SLA than PAT — raise both together
3.3 | VM provisioning and build | Virtual machine built and released to the requesting team | TD Infrastructure | 3 – 5 days per env | 1 | 1.5 | 3.1, 3.2
3.4 | IP assignment, storage allocation and SQL Server installation | Network address, data and log volume sizing, SQL Server install and instance configuration | TD Infrastructure + DBA | 5 days per env | 1 | 2 | 3.3
SERVER ACCESS, CONNECTIVITY AND DATABASE SETUP
3.5 | AD group provisioning for server and database access | Groups for administrators, developers and service accounts across each environment | IAM | 3 – 5 days | 1 | 1.5 | 3.4
3.6 | Firewall requests | Paths from the staging server to Team Connect sources and out to iManage | Network | 5 business day SLA | 1 | 1.5 | 3.4 — per environment
3.7 | DBA setup and standards onboarding | Databases, logins, schemas, backup schedule, HA/DR configuration, monitoring agents and patch windows | DBA | 1 – 2 weeks | 1 | 2 | 3.4, 3.5
3.8 | Server hardening, vulnerability scan and remediation | Baseline hardening, scanning, remediation of findings and security sign-off before data lands | Security + Infrastructure | 1 – 2 weeks | 1 | 2 | 3.4
ADDITIONAL DEVELOPMENT CAUSED BY THE ABSENCE OF A NATIVE ORCHESTRATION ENGINE
3.9 | Build the extraction layer by hand | SSIS packages or custom code for each Team Connect source — on-prem SQL, cloud Oracle and blob — with no managed connectors | TD Dev | +2 – 3 weeks | 2 | 3 | Delivered natively by ADF in Options 1 and 2
3.10 | Build scheduling, retry, logging and lineage | Job scheduler, failure handling, restartability, run history and audit logging all written and maintained by TD | TD Dev | +2 – 3 weeks | 2 | 3 | Delivered natively by ADF in Options 1 and 2
ONGOING RUN COST — PERMANENT, NOT A ONE-OFF
3.11 | Steady-state server ownership | OS patching, SQL Server licensing and version upgrades, capacity management, backup verification and DR testing | TD Infrastructure + DBA | Ongoing | — | — | No equivalent obligation on the PaaS options
SUBTOTAL — ADDITIONAL ENVIRONMENT SETUP: 7 – 11 weeks, PLUS 4 – 6 weeks of extra development
| TOTAL ADDED ENVIRONMENT SETUP |  |  |  | 7 wks | 11 wks | Repeated per environment; PROD carries a 10-day SLA
| PLUS ETL BUILD, TEST AND WAVES — includes the 4 – 6 week hand-built orchestration penalty |  |  |  | 20 wks | 28 wks | 4 – 6 weeks longer than the ADF options
| TOTAL ADDED PROJECT TIME |  |  |  | 26 wks | 38 wks | ≈ 6 – 9 months
| COST VERSUS OPTION 1 |  |  |  | +8 wks | +12 wks | Plus a permanent operational ownership burden
WHEN THIS OPTION MAKES SENSE
This option is only justified if a policy or data-residency constraint rules out Azure PaaS for matter data.
It is slower on the way in (server SLAs of 5 days for PAT and 10 days for PROD, then VM build, SQL install, AD groups,
firewall and DBA onboarding — repeated for every environment) and it costs more on the way out, because TD keeps the OS,
the SQL licence, the patch cycle, the backups and the DR test for as long as the staging database exists.
It also forces TD to hand-build the extraction, scheduling, retry, logging and lineage that Azure Data Factory provides natively.

## 5. ETL Work Steps
Migration Work Steps — Common to All Three Options
The ETL build, validation and wave execution effort. Only Option 3 differs: add 4 – 6 weeks for hand-built orchestration.
ID | Work Step | What It Involves | Accountable Team | Effort (person-days) | Elapsed Low (wks) | Elapsed High (wks) | Dependency
DISCOVERY AND DESIGN
M1 | Team Connect source discovery and data profiling | Identify every source — on-prem SQL, cloud Oracle, blob storage — record counts, volumes, data quality and known gaps | TD Data + Team Connect SMEs | 15 | 2 | 3 | Source system access
M2 | Matter data mapping: Team Connect → iManage | Field-level mapping into an iManage-oriented staging model, including reference data and code value alignment | TD Data + Kroll + business | 20 | 3 | 4 | M1
M3 | Data quality assessment and cleansing rules | Profile defects, define cleansing and enrichment rules, agree what is migrated versus archived versus dropped | TD Data + business | 10 | 2 | 3 | M1
M4 | Staging model design | Design Azure SQL as an iManage-oriented staging and integration model — deliberately NOT a full replica of the Oracle schema | TD Data Architecture | 10 | 1.5 | 2 | M2
M5 | Migration control table design | Batch-level and record-level control tables so every record's position in the migration lifecycle is known at any time | TD Data | 8 | 1 | 1.5 | M4
BUILD
M6 | Extraction pipelines per source | Ingestion from on-prem SQL, cloud Oracle and blob into the RAW layer, with an immutable raw copy retained for replay | TD Dev | 15 | 2 | 3 | M1, environment ready
M7 | Transformation and curation | RAW → CURATED → READY layering, cleansing rules, canonical shaping and business rule application | TD Dev | 20 | 3 | 4 | M2, M3, M6
M8 | Validation, reconciliation and exception reporting | Row counts, referential integrity, mandatory field checks, business rule validation and an exception queue for failures | TD Dev + QA | 15 | 2 | 3 | M7
M9 | Load into iManage | Load the READY layer into iManage via API or bulk import, with per-record status capture and error handling | TD Dev + Kroll | 15 | 2 | 3 | M7, iManage target ready
M10 | Wave orchestration and scheduling | Wave definition, batching, sequencing, restartability and operational scheduling | TD Dev | 8 | 1 | 2 | M5, M9
TEST AND EXECUTION
M11 | Mock migration — cycle 1 | Full dry run through a representative wave, with reconciliation and defect capture | TD QA + Dev | 10 | 2 | 2.5 | M8, M9
M12 | Mock migration — cycle 2 | Second dry run after defect remediation, with formal reconciliation sign-off | TD QA + Dev | 10 | 2 | 2.5 | M11
M13 | Business data validation and UAT | Legal operations validate migrated matters inside iManage against Team Connect source records | Business + TD | 15 | 2 | 3 | M12
M14 | Production wave execution | Execute the migration wave by wave with reconciliation after each — roughly 1 – 2 weeks per wave | TD Dev + business | 5 | 1 | 2 | M13 — per wave
M15 | Post-migration reconciliation and defect remediation | Investigate and re-run failed records, close exception queues, produce the final reconciliation evidence pack | TD Dev + business | 10 | 2 | 3 | M14
M16 | Decommission staging and archive the raw layer | Retire the staging database, archive the immutable raw copy per retention policy, release infrastructure | TD Infrastructure + DBA | 3 | 1 | 1 | M15
| TOTAL ETL BUILD, TEST AND WAVE EXECUTION (with normal parallelism) |  |  | 179 pd | 16 wks | 22 wks | Options 1 and 2
| SAME WORK ON OPTION 3 — add hand-built extraction, scheduling, retry and lineage |  |  | +40 pd | 20 wks | 28 wks | Option 3
EXECUTION APPROACH
Migration runs in waves rather than as one cutover, so wave 1 can go live while later waves are still being transformed.
That is why M14 is shown as 1 – 2 weeks per wave rather than a single block — the total depends on how many waves are agreed.
The raw layer stays immutable so that transformation logic can be re-run without re-extracting from Team Connect.

## 6. Option Comparison
Side-by-Side Option Comparison
Same end state for Options 1 and 2. Option 3 is a different architecture with a permanent ownership cost.
Dimension | Option 1 — ADF in the initial PID | Option 2 — ADF added later | Option 3 — VMCE2 SQL staging | Comment
Added environment setup (elapsed) | 2 – 4 weeks | 8 – 13 weeks | 7 – 11 weeks | Option 1 rides the platform PID and ARE deployment already in flight
ETL build, test and wave execution | 16 – 22 weeks | 16 – 22 weeks | 20 – 28 weeks | Option 3 pays 4 – 6 extra weeks for hand-built orchestration
Total added project time | 18 – 26 weeks (4 – 6 months) | 24 – 36 weeks (5.5 – 8 months) | 26 – 38 weeks (6 – 9 months) | Critical-path elapsed time, not person-effort
Delta versus Option 1 | Baseline | +6 to +10 weeks | +8 to +12 weeks | Option 2's delta is entirely rework
New infrastructure requests required | Integration runtime and firewall only | Full PID, review, CIDR, firewall and ARE cycle again | Server request, VM, SQL install, AD, firewall, DBA — per environment | Each request carries its own queue and SLA
Second security review required | No — covered by the platform CSP review | Yes — delta CSP and privacy review | Yes — plus server hardening and vulnerability remediation | Security review is the highest-variance gate in every option
Orchestration, retry, logging, lineage | Native to Azure Data Factory | Native to Azure Data Factory | Hand-built and TD-maintained | This is the largest hidden cost in Option 3
Connectors to Team Connect sources | Managed connectors for SQL, Oracle and blob | Managed connectors for SQL, Oracle and blob | Custom extraction per source | Team Connect spans on-prem SQL, cloud Oracle and blob storage
Regression risk to the live integration platform | None — deployed together | Yes — landing zone is modified after go-live | Low — separate estate | Option 2 requires a regression pass over production
Ongoing run and ownership cost | Low — PaaS, no OS or licence ownership | Low — same end state as Option 1 | High — OS patching, SQL licensing, backup, DR testing | Option 3's cost never ends
Reusability for future data workloads | High — platform capability from day one | High — same capability, later | Low — single-purpose server | Future integrations and reporting can reuse ADF
Alignment to the recommended architecture | Full | Full | Partial | The recommended design uses ADF for migration and Functions plus Service Bus for operational integration
RECOMMENDATION
Adopt Option 1. Have the Infrastructure Architect include Azure Data Factory, ADLS Gen2 / Blob Storage and the Azure SQL
staging database in the PID being produced for the iManage integration platform, before that PID goes to architecture review.
It costs roughly one week of additional design effort now and saves 6 to 10 weeks later. It also avoids a second security review,
a second network allocation cycle, an ARE redeployment and a regression pass over a live integration platform.
If PaaS is genuinely blocked for matter data, Option 3 remains viable — but it should be chosen deliberately, with the permanent
operational ownership of the server, the SQL licence and the DR obligation understood and accepted up front.

## 7. Assumptions & Risks
Migration Assumptions, Risks and Open Decisions
# | Assumption / Risk | Impact if it does not hold | Likelihood | Mitigation / Owner
ASSUMPTIONS
1 | The integration platform PID has not yet been baselined at architecture review | Option 1 is no longer available and the migration defaults to Option 2 — plus 6 to 10 weeks | Medium | Confirm PID status with the Infrastructure Architect this week — TD Infrastructure
2 | Team Connect data volumes and record counts are known well enough to size the staging database | Sizing rework, storage re-requests and pipeline performance tuning late in the cycle | Medium | Complete source profiling (step M1) before the staging model is finalised
3 | iManage supports a bulk or API-based load of migrated matter data at the required volume | Load throughput becomes the constraint and wave count rises significantly | Medium | Confirm ingestion limits and throttling with Kroll during design — TD Data
4 | Migration is executed in waves rather than as a single cutover | A single cutover concentrates all risk into one window and removes the ability to correct course between waves | Low | Agree wave definitions and sequencing with the business early
5 | On-premises Team Connect sources can be reached from Azure via a self-hosted integration runtime | An alternative extract-and-drop pattern is needed, adding 2 to 3 weeks | Low | Validate the network path during PID design — TD Network
6 | Historical matter data can be transformed into the iManage model without a full Oracle-to-SQL replica | A replica approach would substantially increase scope, storage and transformation effort | Medium | Hold the iManage-oriented staging design — TD Data Architecture
RISKS
7 | The staging decision is deferred past the PID review | The project pays 6 to 10 weeks for an outcome it could have had for free | High | Decide at this meeting — project sponsor
8 | Team Connect data quality is worse than expected | Cleansing scope grows, mock migration cycles increase and UAT sign-off slips | High | Run data profiling (M1) and quality assessment (M3) as early as source access allows
9 | Migration and integration compete for the same TD developers | Both workstreams slow down; the integration go-live and the migration waves collide | High | Separate the resourcing plans or stage the workstreams explicitly — engineering manager
10 | Reconciliation evidence is not defined until late | Business sign-off stalls at the end of the project when it is most expensive to fix | Medium | Agree reconciliation rules and the evidence pack format during design (M8)
11 | Wave count grows during execution | Each additional wave adds 1 to 2 weeks of elapsed time | Medium | Fix wave definitions before the first production wave and manage additions through change control
12 | Option 3 is chosen without accounting for the permanent run cost | TD carries OS patching, SQL licensing, backup verification and DR testing indefinitely | Medium | Include the run cost in the option decision, not just the build cost — TD Infrastructure
DECISIONS NEEDED FROM THIS MEETING
1. Are Azure Data Factory, ADLS/Blob and the Azure SQL staging database going into the initial PID? (Option 1 versus Option 2.)
2. Is there any policy constraint that would force the VMCE2 SQL staging route instead of Azure PaaS?
3. How many migration waves, and what defines each one?
4. Who owns reconciliation sign-off, and what evidence does the business require?
5. Are the migration and integration workstreams sharing developers, and if so which one has priority?