## Work Steps & Timeline
iManage Integration Module — Work Steps, Effort and Timeline
Middleware integration: iManage → Exterro / TyMetrix. Elapsed weeks are calendar time including reviews and queueing, assuming phases run in parallel where they can.
ID | Work Step | Owner | Effort (person-days) | Elapsed Low (wks) | Elapsed High (wks) | On Critical Path? | Gate / Dependency
DESIGN AND DISCOVERY · 4–6 weeks elapsed · same in both build options; Kroll acts as the iManage subject-matter expert
A1 | Confirm integration scope and downstream requirements | TD BA + app teams | 10 | 2 | 3 | Yes | Project kickoff
A2 | iManage API discovery: endpoints, authentication, rate limits, change detection | Kroll (SME) + TD | 10 | 1.5 | 3 | Yes | Kroll SME access
A3 | Field-level mapping: iManage to canonical model to Exterro and TyMetrix | TD + Kroll + vendors | 15 | 2 | 3 | Yes | A1, A2
A4 | Solution design: polling, watermark, idempotency, retry, dead-letter, replay | TD Architecture + Kroll | 15 | 2 | 3 | Yes | A2
A5 | Non-functional requirements: volumes, sync SLA, DR, retention, audit | TD Architecture | 5 | 1 | 1 | No | A1
A6 | Architecture review and design sign-off | TD Architecture | 5 | 2 | 3 | Yes | A4
A7 | SOW / contract change with Kroll for build scope (Kroll option only) | TD Sourcing + Legal | 5 | 2 | 4 | Yes | A6 + build decision
AZURE ENVIRONMENT SETUP · 9–16 weeks elapsed, 6–10 on the critical path · starts at week 1, alongside design and the build; identical in both options
B1 | Submit IAP; Infrastructure Architect assigned | TD Infrastructure | 1 | 0.2 | 0.2 | Yes | Funded project
B2 | IA and Cloud team produce the PID (infrastructure design) | Infra Architect + Cloud | 10 | 1 | 2 | Yes | B1
B3 | Architecture design review of the PID | TD Architecture | 5 | 1 | 2 | Yes | B2
B4 | Cloud CSP security review with Cloud, Network and Privacy teams | Security / Network / Privacy | 15 | 3 | 4 | Yes | B2
B5 | Cloud profile and subscription onboarding | Cloud onboarding | 5 | 1 | 2 | Yes | B3, B4
B6 | CIDR / subnet allocation — 3 business days plus review, per environment (DEV, PAT, PROD) | Network | 9 | 1.8 | 3 | Yes | B5
B7 | AD group provisioning for cloud infrastructure and RBAC mapping | IAM | 5 | 1 | 1.5 | Yes | B5
B8 | Firewall requests for PAT and PROD — 5 business day SLA each | Network | 10 | 1 | 1.5 | Yes | B6
B9 | PAT infrastructure deployment by ARE: resources, NSGs, change tickets (5–8 days) | ARE | 8 | 1 | 1.6 | Yes | B6, B8
B10 | PROD infrastructure deployment by ARE (5–8 days) | ARE | 8 | 1 | 1.6 | Yes | B6, B8
B11 | Key Vault, managed identity, RBAC and secrets onboarding | TD Infrastructure | 5 | 1 | 1.5 | Yes | B9
B12 | Monitoring onboarding: App Insights, Azure Monitor, alert routing to the run team | TD Infrastructure | 5 | 1 | 1.5 | No | B9
B13 | Environment validation and connectivity proving to iManage, Exterro, TyMetrix | TD Infrastructure + Dev | 5 | 1 | 2 | Yes | B9, B10
CODE BUILD · TD 6–8 weeks / Kroll 4–5 weeks · runs in parallel with the environment setup; the only phase the build decision changes
C1 | Repository, CI/CD pipeline and infrastructure-as-code templates (TD-owned in both options) | TD Dev | 10 | 1.5 | 2 | No | B5
C2 | iManage poller: watermark, pagination, throttling, change and delete detection | TD Dev or Kroll | 15 | 2 | 3 | No | A4, C1
C3 | Canonical matter model, normalizer and validation rules | TD Dev or Kroll | 10 | 1.5 | 2 | No | A3
C4 | Service Bus topic, subscriptions, dead-letter and retry policy | TD Dev or Kroll | 5 | 0.6 | 1 | No | A4
C5 | Exterro adapter: mapping, API calls, error handling, retry, status recording | TD Dev or Kroll | 10 | 1.5 | 2 | No | A3, C3
C6 | TyMetrix adapter: mapping, API calls, error handling, retry, status recording | TD Dev or Kroll | 10 | 1.5 | 2 | No | A3, C3
C7 | Integration state store: status, idempotency, correlation IDs, replay | TD Dev or Kroll | 8 | 1 | 1.5 | No | A4
C8 | Manual 'Sync Matter' API via API Management (deferrable out of the MVP) | TD Dev or Kroll | 8 | 1 | 2 | No | C2, C3
C9 | Monitoring instrumentation, dashboards, alerts and runbooks | TD Dev | 8 | 1 | 1.5 | No | B12
C10 | Unit tests and pipeline security gates (SAST, SCA, coverage) | TD Dev or Kroll | 8 | 1 | 1.5 | No | C1
CODE HANDOVER · 4–6 weeks elapsed, 2–4 on the critical path · Kroll option only; partly overlaps the tail of the environment setup
D1 | IP ownership, licensing and source code escrow confirmed | TD Legal + Sourcing | 5 | 1 | 2 | Yes | Code complete
D2 | Code transfer into the TD repository; configuration and secrets moved to Key Vault | TD Dev | 10 | 1.5 | 2.5 | Yes | D1
D3 | TD code review plus SAST, DAST, SCA and licence scanning, with remediation | TD Dev + Security | 10 | 2 | 3 | Yes | D2
D4 | Third-party code risk assessment and approval to run in the TD estate | TD Risk | 5 | 1 | 2 | Yes | D2
D5 | SDLC artefact transfer: design documents, ADRs, test evidence | Kroll to TD | 5 | 1 | 1.5 | No | D2
D6 | Knowledge transfer and shadowing for TD developers and the run team | Kroll to TD | 8 | 2 | 3 | Yes | D3
DEPLOY, TEST AND SUPPORT · 11–13 weeks to go-live, plus 4 weeks hypercare · TD-owned in both options
E1 | Deploy to DEV and PAT through the ARE pipeline with change tickets | TD Dev + ARE | 5 | 1 | 2 | Yes | B9, code complete
E2 | Defect fix and redeploy cycles through PAT | TD Dev (or Kroll) | 8 | 1 | 2 | Yes | E1, F1
E3 | PROD deployment with CAB change approval and implementation window | TD Dev + ARE | 5 | 1 | 1.5 | Yes | B10, F5
E4 | Cutover sequence, initial seed sync, rollback plan and runbook | TD Dev + Run team | 5 | 0.5 | 1 | Yes | E3
F1 | Component and integration testing in PAT against real iManage data | TD QA + Dev | 10 | 2 | 3 | Yes | E1
F2 | End-to-end testing with Exterro and with TyMetrix (vendor coordination, run in parallel) | TD QA + vendors | 20 | 2 | 3 | Yes | F1
F3 | Resilience testing: retry, dead-letter, replay, watermark recovery, duplicates | TD QA + Dev | 5 | 1 | 2 | Yes | F1
F4 | Performance and volume testing, plus security scanning and vulnerability review | TD QA + Security | 10 | 2 | 3 | Yes | F1
F5 | UAT and business sign-off from legal operations | Business + TD | 10 | 2 | 2 | Yes | F2
G1 | Runbooks, alert-to-ticket routing and the on-call model | TD Run team | 5 | 1 | 2 | Yes | C9, E4
G2 | Support model agreement: TD L1/L2 versus Kroll L3 | TD + Kroll | 3 | 1 | 2 | No | Build decision
G3 | Hypercare after go-live (not counted in the time-to-go-live totals below) | TD Dev + Run team | 20 | 4 | 4 | No | E4
G4 | Steady-state ownership: patching, secret rotation, downstream API version changes | TD Run team | Ongoing | — | — | No | G3
| TIME TO GO-LIVE — critical path, TD builds the code |  | ≈ 350 pd | 17 wks | 26 wks | ≈ 4–6 months | Planning midpoint ≈ 5 months
| TIME TO GO-LIVE — critical path, Kroll builds and hands over |  | ≈ 390 pd | 21 wks | 31 wks | ≈ 5–7 months | Planning midpoint ≈ 6 months
HOW TO READ THIS — AND WHAT THE NUMBERS ASSUME
Effort in person-days is work content; elapsed weeks is calendar time including reviews, approvals and queueing. They are not the same.
The totals assume parallel working: the IAP goes in at week 1 so the environment runs alongside design and the code build, and testing
starts in PAT while PROD is still being provisioned. Run these phases end to end instead and the total rises to 8–10 months.
Hypercare (4 weeks) sits after go-live and is excluded from the time-to-go-live totals.
The low end assumes no rework, no security findings and no queue time beyond published SLAs. If the environment setup slips to its
5-month worst case, add roughly 6 weeks to both options.

## TD vs Kroll
Who Writes the Integration Code — TD vs Kroll
Infrastructure, deployment, testing and support are TD-owned in both options. Only the code build differs.
Phase | Scope | Option 1 — TD builds | Option 2 — Kroll builds and hands over | Schedule delta | Comment
Design | Requirements, iManage API discovery, mapping, solution design, architecture sign-off | 4 – 6 weeks | 5 – 7 weeks | +1 wk | Kroll option adds an SOW / contract change before build can start
Environment | IAP, PID, architecture review, Cloud CSP review, CIDR, AD, firewall, ARE deployment | 9 – 16 weeks elapsed (6 – 10 on the critical path) | 9 – 16 weeks elapsed (6 – 10 on the critical path) | 0 | Starts at week 1 alongside design and the build. Kroll building in their own Azure removes none of the TD gates.
Code build | Poller, canonical model, Service Bus, Exterro and TyMetrix adapters, state store | 6 – 8 weeks (0 – 1 on the critical path) | 4 – 5 weeks (0 on the critical path) | −0 to −1 wk | Runs in parallel with the environment setup, so it barely reaches the critical path
Code handover | IP terms, code transfer, TD code review, security scanning, risk approval, knowledge transfer | Not applicable | 4 – 6 weeks (2 – 4 on the critical path) | +2 to +4 wks | Partly overlaps the tail of the environment setup, but cannot start until Kroll finishes
Deployment | PAT and PROD deployment through ARE, CAB approval, cutover | 2 – 3 weeks | 2 – 3 weeks | 0 | TD deploys in both options
Testing | Component, end-to-end with both vendors, resilience, performance, security, UAT | 5 – 6 weeks | 6 – 7 weeks | +1 wk | Testing starts in PAT while PROD is still being provisioned
Hypercare | Runbooks, on-call model, four weeks of hypercare after go-live, transition to run | 4 weeks | 4 weeks | 0 (higher risk) | Sits after go-live, so it is excluded from the totals below
TOTAL | Added time to go-live on the critical path | 17 – 26 weeks (≈ 4–6 months) | 21 – 31 weeks (≈ 5–7 months) | +4 to +5 wks | Kroll building the code does not shorten the project
| Consideration | Option 1 — TD builds | Option 2 — Kroll builds | Advantage | Notes
| Speed to a working module | Slower to write, faster to accept | Faster to write, slower to accept | Neutral | The two effects cancel out
| iManage API expertise | Low — TD does not yet know which APIs will be used | High — Kroll is the platform vendor | Kroll | The strongest argument for the vendor option
| Azure Functions and C# capability | Depends on developer availability | Kroll has delivered on Azure before | Kroll | Confirm named TD developers before deciding
| Long-term supportability | Strong — TD wrote it and can extend it | Weaker — TD inherits unfamiliar code | TD | Every future downstream app extends this codebase
| Cost | Internal capacity, no new spend | Vendor build charges plus internal review effort | TD | The Kroll option pays twice: vendor build and TD review
| Delivery risk if no TD developers are free | High — add 4–8 weeks of ramp-up | Low — vendor resources are contracted | Kroll | This is the scenario that flips the recommendation
| Security and risk | Standard internal SDLC | Third-party code review, IP and escrow obligations | TD | Vendor code in the TD estate carries extra review
Phase |  | Month 1–2 | Month 3–4 | Month 5 | Month 6–7
OPTION 1 — TD BUILDS (planning midpoint ≈ 5 months to go-live)
Design and discovery (4–6 wks)
Azure environment setup (9–16 wks)
Code build (parallel) (6–8 wks)
Deployment (2–3 wks)
Testing and UAT (5–6 wks)
Go-live and hypercare (4 wks)
OPTION 2 — KROLL BUILDS AND HANDS OVER (planning midpoint ≈ 6 months to go-live)
Design plus SOW with Kroll (5–7 wks)
Azure environment setup (9–16 wks)
Kroll code build (parallel) (4–5 wks)
Code handover and TD review (4–6 wks)
Deployment (2–3 wks)
Testing and UAT (6–7 wks)
Go-live and hypercare (4 wks)
RECOMMENDATION — CO-DEVELOPMENT
Kroll writes the integration code inside TD's repository and CI/CD pipeline, with TD engineers embedded from the start.
TD owns the Azure infrastructure, the deployment pipeline, the production release and long-term support.
This captures Kroll's iManage API knowledge while removing the handover, security review and knowledge-transfer gate,
because the code never leaves TD's SDLC. Conditions: at least one TD developer named from the start, and an SOW that fixes
IP ownership, TD coding standards, test evidence requirements and a defect warranty period.
KEY RISKS
No TD developer with Azure Functions and C# experience is free — adds 4–8 weeks and flips the build recommendation.
Cloud CSP review returns material findings — PID rework and a second review cycle, 3–6 weeks.
Phases cannot be run in parallel (no early IAP, no dev subscription) — the totals rise to 8–10 months.
iManage API cannot support reliable change detection — fallback to full scans or scheduled extracts, 3–6 weeks.
Data Factory and staging SQL left out of the initial PID — 6–10 weeks of rework (see the migration workbook).
Queue time beyond published SLAs at the network, IAM and ARE gates — environment slips to 5 months, adding about 6 weeks.