## 1. Summary
iManage Integration Module ¦ Additional Technology Work Effort & Timeline
Middleware integration: iManage → Exterro / TyMetrix — TD build vs. Kroll build comparison
HEADLINE NUMBERS
Added time to go-live | 17 – 26 weeks |  | ≈ 4 – 6 months of additional project time (TD-build scenario)
Azure environment runway | 9 – 16 weeks |  | 2 – 4 months on plan, 5 months as the downside. Unchanged regardless of who writes the code.
Code development effort | 6 – 8 weeks |  | The ONLY phase that differs between the TD and Kroll options.
Net schedule benefit of Kroll building | 0 weeks |  | Dev savings are absorbed by the environment runway and reversed by handover.
KEY FINDINGS FOR THE MEETING
1. The middleware is mandatory. iManage cannot call outbound APIs and neither Exterro nor TyMetrix can pull data, so a TD-hosted
integration module is the only way matter data moves between the three systems. This work is not in the current project plan.
2. Environment setup — not coding — is the critical path. The Azure runway (IAP → PID → CSP → CIDR → AD → firewall → ARE deploy)
is 2–4 months on plan and is identical whether TD or Kroll writes the code. Submitted at week 1 it runs alongside design and
the build, so 6–10 weeks of it lands on the critical path — roughly 35–40% of the total added schedule.
3. Kroll building the code does not shorten the project. Their ~2 week development advantage sits in parallel with the environment
runway (so it barely reaches the critical path), while vendor code handover, TD security review and knowledge transfer add 2–4
weeks that ARE on the critical path.
4. The real question is capability and supportability, not speed. If TD does not have available Azure Functions / C# developers, the
TD-build option gains 4–8 weeks of ramp-up and becomes the slower path.
5. Recommendation: co-development. Kroll writes the integration code inside TD's repository and pipeline with TD engineers embedded
from day one. TD owns the infrastructure, deployment and long-term support. This captures Kroll's iManage API knowledge without
the serial handover gate, which is worth 2–4 weeks on the critical path.
Phase | Scope | TD builds the code (elapsed weeks) | Kroll builds the code (elapsed weeks) | Delta | On critical path? | Comment
A. Design & discovery | Requirements, iManage API discovery, mapping, solution design, architecture sign-off | 4 – 6 | 5 – 7 | +1 | Yes | Kroll option adds SOW / contract change and vendor onboarding
B. Azure environment setup | IAP, PID, architecture review, Cloud CSP review, CIDR, AD groups, firewall, ARE deploy | 6 – 10 | 6 – 10 | 0 | Yes | 9–16 wks elapsed from week 1; only this much lands on the critical path
C. Code build | Poller, canonical model, Service Bus, Exterro / TyMetrix adapters, state store | 0 – 1 | 0 | −0 to −1 | Mostly parallel | Build runs alongside the environment runway; 6–8 wks TD / 4–5 wks Kroll
D. Vendor code handover | IP terms, code transfer, TD code review, SAST/SCA, risk assessment, knowledge transfer | 0 | 2 – 4 | +2 to +4 | Yes | 4–6 wks elapsed; partly overlaps the tail of the environment runway
E. Deployment | DEV/PAT deploy via ARE, defect cycles, PROD change approval, cutover runbook | 2 – 3 | 2 – 3 | 0 | Yes | TD deploys in both options
F. Testing | Component, E2E with Exterro and TyMetrix, resilience, performance, security, UAT | 5 – 6 | 6 – 7 | +1 | Yes | Starts in PAT while PROD is still being provisioned
G. Support & hypercare | Runbooks, alert routing, on-call model, 4 weeks hypercare, steady-state ownership | 4 | 4 | 0 | After go-live | Excluded from the time-to-go-live total below
ADDED TIME TO GO-LIVE (critical path) |  | 17 – 26 wks (4 – 6 months) | 21 – 31 wks (5 – 7 months) | +4 to +5 wks | — | Planning midpoint: TD ≈ 5 months ¦ Kroll ≈ 6 months
HOW TO READ THESE NUMBERS
Totals assume parallel working: the IAP goes in at week 1, so the environment runs alongside design and the build, and testing starts
in PAT while PROD is still being provisioned. Run the phases end to end instead and the total rises to 8–10 months.
Hypercare (4 weeks) follows go-live and is excluded from the totals. If the environment slips to its 5-month worst case, add ~6 weeks.

## 2. Work Steps (All)
Integration Module — Complete Work Breakdown
Every step required to design, build, deploy, test and support the iManage → Exterro / TyMetrix middleware
ID | Work Step | What It Involves | Primary Owner | Effort (person-days) | Elapsed Low (wks) | Elapsed High (wks) | On Critical Path? | Gate / Dependency | Applies To
PHASE A — DESIGN & DISCOVERY (identical in both options; Kroll acts as the iManage subject-matter expert)
A1 | Confirm integration scope and downstream requirements | Which matter attributes Exterro and TyMetrix need, sync frequency, volumes, direction of flow | TD BA + app teams | 10 | 2 | 3 | Yes | Project kickoff | Both options
A2 | iManage API discovery | Identify usable endpoints, authentication model, rate limits, pagination, and what change-detection is actually possible (no native event triggers) | Kroll (SME) + TD | 10 | 1.5 | 3 | Yes | Kroll SME access / SOW | Both options
A3 | Field-level data mapping | iManage → canonical matter model → Exterro contract and TyMetrix contract; reference data and code value alignment | TD + Kroll + vendors | 15 | 2 | 3 | Yes | A1, A2 | Both options
A4 | Integration solution design | Polling strategy and watermark, idempotency, retry, dead-letter, replay, correlation IDs, error classification | TD Architecture + Kroll | 15 | 2 | 3 | Yes | A2 | Both options
A5 | Non-functional requirements | Volume and throughput, sync SLA, availability, DR / RTO / RPO, data retention, logging and audit | TD Architecture | 5 | 1 | 1 | No | A1 | Both options
A6 | TD architecture review and design sign-off | Formal review of the integration pattern and the Azure service selection | TD Architecture | 5 | 2 | 3 | Yes | A4 | Both options
A7 | SOW / contract change with Kroll for code development | Scope, deliverables, acceptance criteria, IP ownership, source code escrow, warranty and defect liability | TD Sourcing + Legal | 5 | 2 | 4 | Yes | A6 + build decision | Kroll option only
PHASE B — AZURE ENVIRONMENT SETUP (identical in both options — TD owns the infrastructure either way)
B1 | Submit IAP and get an Infrastructure Architect assigned | Raise the infrastructure assessment request against the project | TD Infrastructure | 1 | 0.2 | 0.2 | Yes | Funded project + approved design intent | Both options
B2 | IA works with the Cloud team to produce the PID | Platform infrastructure design covering subscription, network, resources, data flows and security controls | Infra Architect + Cloud | 10 | 1 | 2 | Yes | B1 | Both options
B3 | Architecture design review of the PID | Formal architecture governance review and approval of the target Azure design | TD Architecture | 5 | 1 | 2 | Yes | B2 | Both options
B4 | Cloud CSP security review | Joint review with the Cloud, Network and Privacy teams; data classification, egress paths, control mapping and remediation | Security / Network / Privacy | 15 | 3 | 5 | Yes | B2 | Both options
B5 | Cloud profile and subscription onboarding | Subscription, management group placement, policy assignment, tagging and cost centre | Cloud onboarding | 5 | 1 | 2 | Yes | B3, B4 | Both options
B6 | CIDR / subnet allocation — DEV | Network address request plus review (3 business days per environment) | Network | 3 | 0.6 | 1 | Yes | B5 | Both options
B7 | CIDR / subnet allocation — PAT | Network address request plus review (3 business days per environment) | Network | 3 | 0.6 | 1 | Yes | B5 | Both options
B8 | CIDR / subnet allocation — PROD | Network address request plus review (3 business days per environment) | Network | 3 | 0.6 | 1 | Yes | B5 | Both options
B9 | AD group provisioning for cloud infrastructure | Access groups for the platform and for each environment, plus RBAC role mapping | IAM | 5 | 1 | 1.5 | Yes | B5 | Both options
B10 | Firewall request — PAT | Rules to iManage, Exterro, TyMetrix and internal endpoints (5 business day SLA) | Network | 5 | 1 | 1.5 | Yes | B7 | Both options
B11 | Firewall request — PROD | Rules to iManage, Exterro, TyMetrix and internal endpoints (5 business day SLA) | Network | 5 | 1 | 1.5 | Yes | B8 | Both options
B12 | PAT infrastructure deployment by ARE | Resource deployment, network security groups, private endpoints, change tickets (5–8 business days) | ARE | 8 | 1 | 1.6 | Yes | B7, B10 | Both options
B13 | PROD infrastructure deployment by ARE | Resource deployment, network security groups, private endpoints, change tickets (5–8 business days) | ARE | 8 | 1 | 1.6 | Yes | B8, B11 | Both options
B14 | Key Vault, managed identity and secrets onboarding | Vault creation, access policies, managed identity, credential and certificate load, rotation process | TD Infrastructure | 5 | 1 | 1.5 | Yes | B12 | Both options
B15 | Observability onboarding | Application Insights and Azure Monitor workspaces, log retention, alert routing into the run team's ticket queue | TD Infrastructure | 5 | 1 | 1.5 | No | B12 | Both options
B16 | Environment validation and connectivity testing | Prove network paths and authentication to iManage, Exterro and TyMetrix from PAT and PROD | TD Infrastructure + Dev | 5 | 1 | 2 | Yes | B12, B13 | Both options
PHASE C — CODE BUILD (the only phase that changes between the TD and Kroll options)
C1 | Repository, CI/CD pipeline and infrastructure-as-code | Repo and branching standards, build/release pipeline, Bicep or Terraform templates, quality gates. TD-owned in both options. | TD Dev | 10 | 1.5 | 2 | No | B5 | Both options
C2 | iManage poller function | Scheduled polling, durable watermark, pagination, throttling, overlap window handling, change/delete detection | TD Dev or Kroll | 15 | 2 | 3 | No | A4, C1 | Differs by option
C3 | Canonical matter model and normalizer | Mapping iManage records to the internal matter model plus required-field validation and business rules | TD Dev or Kroll | 10 | 1.5 | 2 | No | A3 | Differs by option
C4 | Service Bus topic, subscriptions and dead-letter handling | matter-events topic, per-application subscriptions, retry policy, DLQ and replay tooling | TD Dev or Kroll | 5 | 0.6 | 1 | No | A4 | Differs by option
C5 | Exterro adapter | Canonical → Exterro mapping, API calls, Exterro-specific error handling, transient retry, status recording | TD Dev or Kroll | 10 | 1.5 | 2 | No | A3, C3 | Differs by option
C6 | TyMetrix adapter | Canonical → TyMetrix mapping, API calls, TyMetrix-specific error handling, transient retry, status recording | TD Dev or Kroll | 10 | 1.5 | 2 | No | A3, C3 | Differs by option
C7 | Integration state store | Azure SQL schema for integration status, idempotency keys, correlation IDs, retry counts and replay support | TD Dev or Kroll | 8 | 1 | 1.5 | No | A4 | Differs by option
C8 | Manual 'Sync Matter' API (API Management + function) | UI-triggered sync from iManage entering the same downstream pipeline. Can be deferred out of the MVP. | TD Dev or Kroll | 8 | 1 | 2 | No | C2, C3 | Differs by option
C9 | Observability instrumentation and runbooks | Custom telemetry, end-to-end correlation, dashboards, alert thresholds and operational runbooks | TD Dev | 8 | 1 | 1.5 | No | B15 | Both options
C10 | Unit tests and pipeline security gates | Unit and component tests, SAST, SCA / open-source scanning, code coverage thresholds | TD Dev or Kroll | 8 | 1 | 1.5 | No | C1 | Differs by option
PHASE D — VENDOR CODE HANDOVER (Kroll option only — serial, and it sits directly on the critical path)
D1 | IP ownership, licensing and source code escrow confirmed | Confirm TD owns or is licensed for the delivered code and any third-party libraries used | TD Legal + Sourcing | 5 | 1 | 2 | Yes | Code complete | Kroll option only
D2 | Code transfer into TD repository and pipeline | Move source into TD SCM, externalise configuration and secrets to Key Vault, align to TD IaC and pipeline standards | TD Dev | 10 | 1.5 | 2.5 | Yes | D1 | Kroll option only
D3 | TD code review and security scanning | Peer review against TD coding standards plus SAST, DAST, SCA and open-source licence scanning, with remediation cycles | TD Dev + Security | 10 | 2 | 3 | Yes | D2 | Kroll option only
D4 | Third-party code risk assessment | Vendor-delivered code risk review and approval to run in the TD estate | TD Risk | 5 | 1 | 2 | Yes | D2 | Kroll option only
D5 | SDLC artefact transfer | Design documents, architecture decision records, test evidence and traceability loaded into TD tooling | Kroll → TD | 5 | 1 | 1.5 | No | D2 | Kroll option only
D6 | Knowledge transfer and shadowing | Sessions for TD developers and the run team so TD can support, patch and extend the code | Kroll → TD | 8 | 2 | 3 | Yes | D3 | Kroll option only
PHASE E — DEPLOYMENT (TD-owned in both options)
E1 | Deploy to DEV / PAT via the ARE pipeline | Release build, configuration per environment, change tickets and deployment verification | TD Dev + ARE | 5 | 1 | 2 | Yes | B12, code complete | Both options
E2 | Defect fix and redeploy cycles | Iterations through PAT as integration and E2E defects are found and fixed | TD Dev (or Kroll) | 8 | 1 | 2 | Yes | E1, F1 | Both options
E3 | PROD deployment and CAB change approval | Production release package, change record, CAB approval and implementation window | TD Dev + ARE | 5 | 1 | 1.5 | Yes | B13, F7 | Both options
E4 | Cutover, rollback plan and runbook | Go-live sequence, initial backfill or seed sync, rollback procedure and support handover pack | TD Dev + Run team | 5 | 0.5 | 1 | Yes | E3 | Both options
PHASE F — TESTING
F1 | Component and integration testing in PAT | Poller, normalizer, Service Bus routing and adapters tested against real iManage PAT data | TD QA + Dev | 10 | 2 | 3 | Yes | E1 | Both options
F2 | End-to-end testing with Exterro | Full matter lifecycle through to Exterro, with vendor coordination and test data alignment | TD QA + Exterro | 10 | 2 | 3 | Yes | F1 | Both options
F3 | End-to-end testing with TyMetrix | Full matter lifecycle through to TyMetrix, with vendor coordination and test data alignment | TD QA + TyMetrix | 10 | 2 | 3 | Yes | F1 | Both options
F4 | Resilience and failure testing | Retry behaviour, dead-letter handling, replay, watermark recovery, duplicate suppression, downstream outage simulation | TD QA + Dev | 5 | 1 | 2 | Yes | F1 | Both options
F5 | Performance and volume testing | Peak matter volume, polling frequency, API throttling behaviour and backlog drain rate | TD QA | 5 | 1 | 2 | No | F1 | Both options
F6 | Security testing | Vulnerability scanning, secrets handling review, and penetration testing if any endpoint is externally reachable | TD Security | 5 | 2 | 3 | Yes | E1 | Both options
F7 | UAT and business sign-off | Legal operations validation of matter data quality in Exterro and TyMetrix, and formal go-live approval | Business + TD | 10 | 2 | 3 | Yes | F2, F3 | Both options
PHASE G — SUPPORT AND TRANSITION TO RUN
G1 | Runbooks, alert-to-ticket routing and on-call model | Operational documentation, monitoring thresholds, escalation paths and support rota | TD Run team | 5 | 1 | 2 | Yes | C9, E4 | Both options
G2 | Support model agreement | Who fixes what: TD L1/L2 versus Kroll L3 for the integration code and for the iManage platform itself | TD + Kroll | 3 | 1 | 2 | No | Build decision | Both options
G3 | Hypercare | Elevated support after go-live: daily monitoring, rapid defect turnaround, tuning of polling and retry settings | TD Dev + Run team | 20 | 4 | 4 | Yes | E4 | Both options
G4 | Steady-state ownership | Patching, certificate and secret rotation, iManage / Exterro / TyMetrix API version changes, capacity and cost management | TD Run team | Ongoing | — | — | No | G3 | Both options
NOTES
Effort (person-days) is the work content. Elapsed weeks is calendar time including queueing, reviews and approvals — the two are not the same.
Phase C elapsed totals 6–8 weeks for TD and 4–5 weeks for Kroll, but it runs in parallel with Phase B, so most of it never reaches the critical path.
Phase D exists only if Kroll writes the code. It cannot start until development is finished, which is why it lands squarely on the critical path.

## 3. Azure Infra Runway
Azure Environment Runway — The Longest Single Workstream
2 to 4 months on plan before code can be deployed. Runs from week 1 alongside design and the build. Identical in both build options.
Seq | Gate / Activity | Accountable Team | Published SLA / Duration | Elapsed Low (wks) | Elapsed High (wks) | What Blocks If This Slips | Repeats Per Environment?
1 | Submit IAP request — Infrastructure Architect assigned | TD Infrastructure | 1 business day | 0.2 | 0.2 | Nothing starts — this is the entry gate to the whole runway | No
2 | IA and Cloud team produce the PID (infrastructure design) | Infra Architect + Cloud | 1 – 2 weeks | 1 | 2 | No design means no security review and no build request | No
3 | Architecture design review of the PID | TD Architecture | 1 – 2 weeks | 1 | 2 | PID cannot be baselined; downstream requests are rejected | No
4 | Cloud CSP security review (Cloud, Network, Privacy) | Security / Network / Privacy | 3 – 4 weeks | 3 | 4 | Highest-variance gate. Findings force PID rework and a re-review. | No
5 | Cloud profile / subscription onboarding | Cloud onboarding | 1 – 2 weeks | 1 | 2 | No subscription means no resources can be created | No
6 | CIDR / subnet allocation | Network | 3 business days + review | 0.6 | 1 | No addressing means no NSGs, no private endpoints, no deployment | Yes — DEV, PAT, PROD
7 | AD group provisioning for cloud infrastructure | IAM | 1 week | 1 | 1.5 | Team cannot access the environment they are waiting on | Partly — per environment role
8 | Firewall requests — PAT and PROD | Network | 5 business day SLA | 1 | 1.5 | No connectivity to iManage, Exterro or TyMetrix | Yes — PAT and PROD
9 | PAT infrastructure deployment by ARE | ARE | 5 – 8 business days | 1 | 1.6 | No test environment — all testing stops | Yes
10 | PROD infrastructure deployment by ARE | ARE | 5 – 8 business days | 1 | 1.6 | No production target — go-live cannot happen | Yes
11 | Key Vault, managed identity, RBAC and secrets onboarding | TD Infrastructure | 1 – 1.5 weeks | 1 | 1.5 | Credentials cannot be stored or rotated to standard | Yes
12 | Environment validation and connectivity proving | TD Infrastructure + Dev | 1 – 2 weeks | 1 | 2 | Integration testing cannot begin | Yes
| TOTAL AZURE RUNWAY (with normal parallelism) |  |  | 9 wks | 16 wks | ≈ 2–4 months on plan; 5 months worst case
WHY THIS IS THE LONGEST POLE — AND THE ONE THING TO FIX TODAY
The runway is gated end to end: IAP → architecture review → cloud profile → CIDR approval → firewall → ARE provisioning.
Submit the IAP at week 1 so this runs alongside design and the code build — that overlap is what keeps the project at 4–6 months.
Each gate has its own queue, and a finding at the Cloud CSP review sends the PID back to the start of the design loop.
Every environment (DEV, PAT, PROD) repeats the addressing, firewall and deployment steps — three environments, not one.
ACTION: include Azure Data Factory, ADLS/Blob and the Azure SQL staging database in this PID now. Adding them afterwards
costs an additional 6–10 weeks of PID rework and ARE redeployment (see the Team Connect migration workbook, Option 2).

## 4. TD vs Kroll
Decision Point — Who Writes the Integration Code?
Infrastructure, deployment, testing and support are TD-owned in both options. Only the code build differs.
Step | Activity | Option 1 — TD builds the code | Option 2 — Kroll builds and hands over code | Schedule delta | Why
A | Design, iManage API discovery and data mapping | 4 – 6 weeks. Kroll engaged as SME under the existing agreement. | 5 – 7 weeks. Same design work plus an SOW / contract change for build scope. | +1 wk | Contracting, IP terms and acceptance criteria must be settled before Kroll can start.
B | Azure environment setup (IAP → PID → CSP → CIDR → firewall → ARE) | 9 – 16 weeks elapsed, 6 – 10 on the critical path. | 9 – 16 weeks elapsed, 6 – 10 on the critical path. | 0 | Starts at week 1 alongside design. Kroll building in their own Azure removes no TD gate.
C | Code development | 6 – 8 weeks. TD developers, with a learning curve on the iManage API and on Azure Functions / Service Bus. | 4 – 5 weeks. Kroll already knows the iManage API surface and has done this pattern before. | −2 to −3 wks | Real saving — but it runs in parallel with the environment runway, so it rarely reaches the critical path.
D | Code handover, security review and knowledge transfer | Not applicable. Code is written inside TD's repository and pipeline from day one. | 4 – 6 weeks elapsed, 2 – 4 on the critical path. IP terms, code transfer, TD code review, SAST / SCA, risk approval, KT. | +2 to +4 wks | Partly overlaps the tail of the environment runway, but cannot start until Kroll finishes.
E | Deployment to PAT and PROD | 2 – 3 weeks. TD deploys through ARE and CAB. | 2 – 3 weeks. TD still deploys — Kroll cannot deploy into the TD estate. | 0 | Deployment rights and change management stay with TD in every scenario.
F | Testing (component, E2E, resilience, security, UAT) | 5 – 6 weeks, starting in PAT while PROD is provisioned. | 6 – 7 weeks. Defect fixes route back to the vendor and return through review. | +1 wk | Every vendor defect fix repeats a slice of the code review and scanning cycle.
G | Hypercare and transition to run | 4 weeks. Team supports code it wrote. | 4 weeks, but with materially higher risk. TD supports code it did not write. | 0 (higher risk) | Mean time to repair rises when the run team's first exposure to the code was a KT deck.
| ADDED TIME TO GO-LIVE (critical path) | 17 – 26 weeks (≈ 4 – 6 months) | 21 – 31 weeks (≈ 5 – 7 months) | +4 to +5 wks | Kroll building the code does not shorten the project.
| Consideration | Option 1 — TD builds | Option 2 — Kroll builds | Advantage | Notes
| Speed to a working module | Slower to write, faster to accept | Faster to write, slower to accept | Neutral | The two effects cancel out almost exactly.
| iManage API expertise | Low — TD does not yet know which APIs will be used | High — Kroll is the platform vendor | Kroll | This is the single strongest argument for the vendor option.
| Azure Functions / Service Bus capability | Depends entirely on developer availability | Kroll has delivered on Azure before | Kroll | Confirm TD developer availability before committing to Option 1.
| Long-term supportability | Strong — TD wrote it and can extend it | Weaker — TD inherits unfamiliar code | TD | Every future downstream application is an extension of this codebase.
| Cost | Internal capacity, no new spend | Vendor development charges plus TD review effort | TD | TD also pays twice in the Kroll option: vendor build plus internal review.
| Delivery risk if TD has no free developers | High — add 4 – 8 weeks of ramp-up or hiring | Low — vendor resources are contracted | Kroll | This is the scenario that flips the recommendation.
| Security and risk posture | Standard internal SDLC | Third-party code review, IP and escrow obligations | TD | Vendor code in the TD estate carries mandatory additional review.
| Extensibility to future downstream apps | TD adds a Service Bus subscription and an adapter itself | TD must either learn the code or re-engage Kroll each time | TD | Exterro and TyMetrix are the first two of many.
RECOMMENDATION — OPTION 3: CO-DEVELOPMENT
Kroll writes the integration code INSIDE TD's repository and CI/CD pipeline, with TD engineers embedded from day one.
TD owns the Azure infrastructure, the deployment pipeline, the production release and the long-term support model.
Why: it captures Kroll's iManage API knowledge (the genuine gap) while deleting the 4–6 week serial handover, security review
and knowledge-transfer gate worth 2–4 critical-path weeks — TD engineers are already inside the codebase and the code never
leaves TD's SDLC.
Conditions: TD assigns at least one developer to the build from the start, and the SOW fixes IP ownership, coding standards,
test evidence requirements and a defect warranty period up front.

## 5. Timeline View
Indicative Timeline — Both Options Side by Side
Months from project approval. Shaded cells show where each phase sits; both scenarios use planning midpoints.
Phase | Elapsed | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
SCENARIO 1 — TD BUILDS THE CODE (planning midpoint ≈ 5 months to go-live)
A. Design, API discovery, mapping, architecture sign-off | 4 – 6 wks
B. Azure environment runway (IAP → PID → CSP → ARE) | 9 – 16 wks
C. Code build (parallel to the environment runway) | 6 – 8 wks
E. Deployment to PAT and PROD | 2 – 3 wks
F. Testing — component, E2E, resilience, security, UAT | 5 – 6 wks
G. Go-live and hypercare | 4 wks
SCENARIO 2 — KROLL BUILDS AND HANDS OVER THE CODE (planning midpoint ≈ 6 months to go-live)
A. Design + SOW / contract change with Kroll | 5 – 7 wks
B. Azure environment runway (unchanged) | 9 – 16 wks
C. Kroll code build (parallel to the environment runway) | 4 – 5 wks
D. Code handover, TD review, security scan, KT | 4 – 6 wks
E. Deployment to PAT and PROD | 2 – 3 wks
F. Testing (extra vendor defect round-trips) | 6 – 7 wks
G. Go-live and hypercare | 4 wks
WHAT THIS CHART SHOWS
The single red band — vendor code handover — is what pushes Scenario 2 roughly four to five weeks past Scenario 1.
It exists only because the code was written outside TD's SDLC. The co-development recommendation removes it entirely.
Both scenarios are dominated by the same dark green band: the Azure environment runway, which no build option shortens.
Both assume the IAP goes in at week 1 so the runway overlaps design and the build. Run them end to end and add 8–12 weeks.

## 6. Assumptions & Risks
Assumptions, Risks and Open Decisions
# | Risk / Assumption | Impact if it does not hold | Likelihood | Mitigation / Owner
ASSUMPTIONS BEHIND EVERY ESTIMATE IN THIS WORKBOOK
1 | The iManage API exposes a usable change / last-modified query and supports the required authentication model | No polling-based change detection is possible; the design would have to fall back to full scans or scheduled extracts, adding 3–6 weeks | Medium | Confirm with Kroll during Phase A before the design is baselined — TD Architecture
2 | Exterro and TyMetrix expose write APIs suitable for per-matter updates, or accept a defined batch file | Adapter design changes and vendor engagement is required; add 2–4 weeks per downstream system | Medium | Obtain both API specifications during Phase A — TD BA
3 | The IAP goes in at week 1 and a dev or sandbox subscription is available, so design and coding run alongside the environment runway | The phases become serial and the total rises to 8–10 months in both options | Medium | Submit the IAP at project start and request a dev subscription in it — TD Infrastructure
4 | Published SLAs are met and there is no queue time beyond them at the network, IAM and ARE gates | Every week of queue time is a week of project slip; the 5-month worst case assumes moderate queuing | High | Raise all requests as early as the dependency allows — project manager
5 | The Cloud CSP review passes with no material findings and the environment lands at 2–4 months rather than 5 | PID rework plus a second review cycle adds 3–6 weeks; a 5-month environment adds about 6 weeks | Medium | Pre-socialise the design with Security, Network and Privacy before formal submission
6 | TD developers with Azure Functions, Service Bus and C# / .NET experience are available for the build | Option 1 gains 4–8 weeks of ramp-up or hiring and becomes the slower path | High | Confirm named resources before the build decision is made — engineering manager
DELIVERY RISKS
7 | This integration work is not in the approved project plan or budget | Funding and resourcing decisions become a schedule dependency in their own right | High | Take the estimate to the steering committee at the next checkpoint — project sponsor
8 | TD ends up supporting integration code it did not write (Kroll option) | Longer mean time to repair, dependency on the vendor for every defect and every future downstream application | High | Co-development, or a contracted L3 support agreement with defined response times
9 | Scope grows as more downstream applications are added after go-live | Each new application is a new adapter and subscription — modest if the canonical model holds, expensive if it does not | Medium | Hold the canonical matter model and adapter pattern; do not allow point-to-point shortcuts
10 | The manual 'Sync Matter' capability from the iManage UI is treated as mandatory for go-live | API Management is pulled into the MVP, adding design, security review and 1–2 weeks of build | Medium | Confirm with the business whether manual sync is day-one or a fast-follow — TD BA
11 | Vendor lock-in on integration knowledge | Every future change requires a Kroll engagement and a commercial cycle | Medium | Mandatory knowledge transfer and TD-owned documentation as an SOW deliverable
12 | The Team Connect migration ADF and staging database are left out of the initial PID | 6–10 weeks of PID rework and ARE redeployment later in the project | High | Add them to the PID scope now — see the migration workbook — Infrastructure Architect
DECISIONS NEEDED FROM THIS MEETING
1. Who writes the integration code — TD, Kroll, or co-development? (Drives the SOW and the resourcing plan.)
2. Are Azure Data Factory and the Azure SQL staging database in the initial PID? (Decide before the PID is baselined.)
3. Is the manual 'Sync Matter' action from the iManage UI in scope for go-live or a fast-follow?
4. Which TD developers are named for this build, and from what date?
5. Who owns L3 support for the integration module after hypercare?