## Slide 1
TD
TECHNOLOGY SOLUTIONS
iManage Integration Module
Additional technology work, effort and timelines
4–6
months added
to the project
2–4
months to build
the Azure environment
6–8
weeks of code
development
Notes: Purpose: agree the work, the schedule impact and who writes the integration code.

## Slide 2
BACKGROUND
Why we need an integration module
None of the three systems can move data on their own.
iManage
Matter system
TD-hosted
integration module
(Azure)
Exterro
TyMetrix
Future downstream apps
poll for change
push
iManage
No event triggers and no ability to call outbound APIs. It exposes an endpoint that can be pinged.
Exterro and TyMetrix
Cannot send or request data. Both accept batch intake, but something has to assemble and deliver the batch.
Result
A TD-hosted integration module is the only way matter data moves between the three systems.
iManage Integration Module | Technology Solutions
2

## Slide 3
TARGET ARCHITECTURE
Recommended Azure platform
Azure Functions and Service Bus for the integration. Data Factory for the Team Connect migration.
INTEGRATION
iManage
Function: poller
API Mgmt: manual sync
Functions:
canonical model
Service Bus
matter-events
Exterro adapter → Exterro
TyMetrix adapter → TyMetrix
Future adapters
Supporting services: Azure SQL (integration state) · Key Vault (secrets) · Application Insights and Azure Monitor (monitoring)
MIGRATION
Team Connect
(SQL / Oracle / blob)
Azure Data Factory
ingest & transform
ADLS / Blob
RAW → CURATED → READY
Azure SQL
iManage staging
iManage
migration waves
Why not Data Factory for the integration
Data Factory is an ETL tool. A pipeline calling Exterro, then TyMetrix, then the next app absorbs every app's mapping, retry and routing logic.
Scope for the MVP
Functions, Service Bus, Azure SQL, Key Vault and App Insights. Defer API Management unless manual sync from the iManage UI is needed at go-live.
iManage Integration Module | Technology Solutions
3
Notes: If asked whether this is too much: the same IAP, PID, security review and ARE deployment apply to a simpler design, so a design that cannot take the third and fourth downstream app means paying the environment runway twice.

## Slide 4
WORK STEPS · 1 OF 2
Design and environment setup
Same in both build options. Kroll is the iManage subject-matter expert throughout design.
Step | Owner | Elapsed | Gate / dependency
DESIGN AND DISCOVERY (4–6 weeks) |  |  | 
Confirm integration scope and downstream requirements | TD BA + app teams | 2–3 wks | Project kickoff
iManage API discovery: endpoints, auth, rate limits, change detection | Kroll (SME) + TD | 1.5–3 wks | Kroll SME access
Field-level mapping: iManage to canonical model to Exterro / TyMetrix | TD + Kroll + vendors | 2–3 wks | Scope, API discovery
Solution design: polling, watermark, idempotency, retry, replay | TD Architecture + Kroll | 2–3 wks | API discovery
Architecture review and design sign-off | TD Architecture | 2–3 wks | Solution design
SOW / contract change with Kroll (Kroll option only) | TD Sourcing + Legal | 2–4 wks | Build decision
AZURE ENVIRONMENT SETUP (9–16 weeks · starts at week 1, alongside design and the build) |  |  | 
IAP submission, PID production, architecture review | TD Infra + IA + Cloud | 2–3 wks | Funded project
Cloud CSP security review: Cloud, Network and Privacy teams | Security / Network / Privacy | 3–4 wks | PID issued
Cloud profile onboarding, CIDR allocation, AD group provisioning | Cloud + Network + IAM | 2–3 wks | Reviews passed
Firewall requests and ARE deployment: PAT then PROD | Network + ARE | 3–4 wks | CIDR approved
Key Vault, managed identity, monitoring, connectivity proving | TD Infrastructure | 1–2 wks | ARE deployment
iManage Integration Module | Technology Solutions
4

## Slide 5
WORK STEPS · 2 OF 2
Build, deploy, test and support
The build is the only part the vendor decision changes. Handover applies only if Kroll writes the code.
Step | Owner | Elapsed | On critical path?
CODE BUILD (TD 6–8 weeks · Kroll 4–5 weeks · runs in parallel with the environment setup) |  |  | 
Repository, CI/CD pipeline and infrastructure-as-code templates | TD Dev (TD-owned either way) | 1.5–2 wks | No
iManage poller: watermark, pagination, throttling, change detection | TD Dev or Kroll | 2–3 wks | No
Canonical matter model, normalizer and validation rules | TD Dev or Kroll | 1.5–2 wks | No
Service Bus topic, subscriptions, dead-letter and retry policy | TD Dev or Kroll | 0.5–1 wk | No
Exterro adapter and TyMetrix adapter: mapping, API calls, retry | TD Dev or Kroll | 3–4 wks | No
Integration state store: status, idempotency, correlation, replay | TD Dev or Kroll | 1–1.5 wks | No
Monitoring instrumentation, dashboards and runbooks | TD Dev | 1–1.5 wks | No
CODE HANDOVER (4–6 weeks elapsed · 2–4 weeks on the critical path · Kroll option only) |  |  | 
IP ownership, licensing and source code escrow confirmed | TD Legal + Sourcing | 1–2 wks | Yes
Code transfer into TD repository, secrets moved to Key Vault | TD Dev | 1.5–2.5 wks | Yes
TD code review, SAST / DAST / SCA scanning and remediation | TD Dev + Security | 2–3 wks | Yes
Third-party code risk assessment and knowledge transfer | TD Risk · Kroll to TD | 2–3 wks | Yes
DEPLOY, TEST AND SUPPORT (11–13 weeks · TD-owned in both options) |  |  | 
Deploy to PAT and PROD through ARE, with CAB approval and cutover | TD Dev + ARE | 2–3 wks | Yes
Testing: component, end-to-end with Exterro and TyMetrix, resilience, security | TD QA + vendors | 4–5 wks | Yes
UAT and business sign-off | Business + TD | 2 wks | Yes
Hypercare, runbooks and transition to the run team (after go-live) | TD Dev + Run team | 4 wks | No
iManage Integration Module | Technology Solutions
5

## Slide 6
ENVIRONMENT SETUP
Azure environment: 2 to 4 months
Submitted at week 1, this runs alongside design and the code build. Every gate is the same whether TD or Kroll writes the code.
1
Submit IAP · Infrastructure Architect assigned
1 day
2
IA and Cloud team produce the PID
1–2 wks
3
Architecture design review of the PID
1–2 wks
4
Cloud CSP review: Cloud, Network, Privacy
3–4 wks
5
Cloud profile and subscription onboarding
1–2 wks
6
CIDR / subnet allocation, per environment
3 days each
7
AD group provisioning for cloud infrastructure
1 wk
8
Firewall requests: PAT and PROD
5-day SLA
9
PAT infrastructure deployment by ARE
5–8 days
10
PROD infrastructure deployment by ARE
5–8 days
11
Key Vault, managed identity, secrets onboarding
1–1.5 wks
12
Environment validation and connectivity proving
1–2 wks
9 – 16 weeks
On plan, with 22 weeks as the downside if a review repeats. Because it starts at week 1, only 6–10 weeks of it sits on the critical path.
Include the migration services in this PID
Data Factory, ADLS/Blob and the Azure SQL staging database. Adding them after the PID is baselined costs 6–10 weeks of rework.
iManage Integration Module | Technology Solutions
6

## Slide 7
DECISION
Who writes the integration code
This covers the application code only. TD owns the infrastructure, the deployment and production support in both options.
OPTION 1
TD builds
Development
6–8 weeks. Learning curve on the iManage API and on Azure Functions.
Handover
None. The code is written in TD's repository from the start.
Support
TD supports and extends code it wrote.
Main risk
Developer availability. Add 4–8 weeks if no one with Azure Functions and C# experience is free.
OPTION 2
Kroll builds and hands over
Development
4–5 weeks. Kroll knows the iManage API and has delivered on Azure.
Handover
4–6 weeks elapsed, 2–4 of them on the critical path. IP terms, code transfer, TD code review, scanning, knowledge transfer.
Support
TD supports code it did not write.
Main risk
Handover is serial and sits on the critical path, so it adds more than the build saves.
TD builds
≈ 21 weeks
Kroll builds
≈ 26 weeks
Difference
+ 5 weeks
Kroll's two-week build advantage runs in parallel with the environment setup, so it does not shorten the project. The handover it creates does extend it.
iManage Integration Module | Technology Solutions
7
Notes: Decide on capability and long-term support, not on schedule. The end date barely moves either way.

## Slide 8
TIMELINE
Schedule impact by phase
Elapsed weeks on the critical path, using planning midpoints. Hypercare adds a further 4 weeks after go-live.
Chart: Elapsed weeks on the critical path
| Testing & UAT | Deployment | Code handover | Code build (on critical path) | Azure environment (on critical path) | Design & discovery
TD builds the code | 5.5 | 2.5 | 0 | 0.5 | 8 | 5
Kroll builds and hands over | 6.5 | 2.5 | 3 | 0 | 8 | 6
17–26 weeks
added to go-live if TD writes the code (4 to 6 months)
6–10 weeks
the part of the environment setup that lands on the critical path
6–8 weeks
code development, the only part the decision changes
Top risks
No TD developer free: add 4–8 wks
Security review repeats: add 3–6 wks
Environment slips to 5 months: add 6 wks
iManage Integration Module | Technology Solutions
8

## Slide 9
SUMMARY
Recommendations
Six decisions, side by side. Detail and step-level timings are in the two supporting workbooks.
Topic | Recommendation | Why | Cost of not doing it
Integration platform | Azure Functions + Service Bus, not Data Factory | Data Factory is built for ETL. The integration needs polling, retry, dead-letter and per-application routing. | One pipeline absorbs every application's logic and is redesigned each time an app is added.
Who writes the code | Co-development: Kroll writes it in TD's repository with TD engineers embedded | Gets Kroll's iManage API knowledge without a 4–6 week handover, and TD can support the code afterwards. | Either 4–8 weeks of TD ramp-up, or 2–4 weeks of handover on the critical path.
Infrastructure and support | TD owns the Azure environment, pipeline, deployment and production support | The module runs in TD's tenancy. Kroll building in their own Azure removes none of the TD gates. | Not applicable — this holds in every option.
MVP scope | Defer API Management unless manual sync from the iManage UI is needed at go-live | Everything else in the MVP is needed for retry, replay and a second downstream system. | 1–2 weeks of build plus an extra design and security review cycle.
Migration staging | Name Data Factory, ADLS/Blob and Azure SQL staging in the initial PID | They are then provisioned in the same ARE deployment as the integration platform. | 6–10 weeks of PID rework, a second security review and an ARE redeployment.
Timing | Submit the IAP now and name the TD developers | The 2–4 month environment runway starts at IAP submission, not at design sign-off. | Every week of delay moves the end date by a week.
Decisions needed today: who writes the code · are the migration services in the PID · which developers are named · is manual sync in scope for go-live · when is the IAP submitted
iManage Integration Module | Technology Solutions
9