## Slide 1
TD
TECHNOLOGY SOLUTIONS | FOR DISCUSSION
iManage Integration Module
Additional technology development work, effort and timeline
iManage → Exterro / TyMetrix · Azure integration platform · Build-vs-vendor decision
4–6
months added
to the project
2–4
months for the
Azure environment
1
decision needed
today
Notes: Framing: this integration work is not in the approved plan. Three things to land today - the work required, the schedule impact, and who writes the code.

## Slide 2
PURPOSE OF THIS SESSION
What we need to land today
Five items. The first three are context; the last two are decisions that change the plan.
1
Why a middleware module is unavoidable
iManage cannot call out. Exterro and TyMetrix cannot pull. Something in the middle has to push.
2
What the platform looks like
Azure Functions and Service Bus for operational integration; Data Factory for the migration.
3
Everything that has to happen
Design, environment, build, deploy, test, support — full step list with owners and durations.
4
How much time this adds
4 to 6 months, and roughly half of it is environment provisioning, not coding.
5
Who writes the code — TD or Kroll
The decision point. Infrastructure, deployment and support stay with TD either way.
iManage Integration Module | Technology Solutions | For discussion
2

## Slide 3
THE CONSTRAINT
Why a middleware module is unavoidable
None of the three systems can move data on their own. This is an architectural constraint, not a preference.
iManage
Matter system
TD-hosted
integration module
(Azure)
Exterro
TyMetrix
Future downstream apps
poll for change
push
iManage
No event triggers and no ability to call outbound APIs. It exposes an endpoint that can be pinged — nothing more.
Exterro & TyMetrix
Cannot send or request data. Both support batch intake, but something still has to assemble and deliver the batch.
The consequence
A TD-hosted middleware module is the only mechanism that moves matter data between the three systems.
iManage Integration Module | Technology Solutions | For discussion
3
Notes: Key point: this is not a design preference. Without the middleware there is no data flow at all between iManage and the downstream applications.

## Slide 4
SCOPE OF THE ADDITIONAL WORK
Seven phases of work, only one of which is coding
Phase D applies only if Kroll writes the code. Everything else happens regardless.
A
Design &
discovery
4–6 wks
›
B
Azure
environment
9–16 wks
›
C
Code
build
6–8 wks
›
D
Vendor
handover
4–6 wks
›
E
Deploy to
PAT & PROD
2–3 wks
›
F
Testing
& UAT
5–6 wks
›
G
Hypercare
& run
4 wks
D · Kroll option only
1
Environment setup is the critical path
Phase B is 35–40% of the added schedule and is identical no matter who writes the code.
2
Coding runs in parallel
Phase C sits alongside Phase B, so the build barely reaches the critical path at all.
3
Only Phase C changes with the vendor decision
And Phase D — the handover it creates — costs more than Phase C saves.
iManage Integration Module | Technology Solutions | For discussion
4

## Slide 5
TARGET ARCHITECTURE
The recommended Azure integration platform
Two workloads, deliberately separated: operational integration, and the Team Connect migration.
OPERATIONAL INTEGRATION — Azure Functions + Service Bus
iManage
Function: poller
API Mgmt: manual sync
Functions:
canonical model
Service Bus
matter-events
Exterro adapter → Exterro
TyMetrix adapter → TyMetrix
Future adapters
Supporting services: Azure SQL (integration state and idempotency) · Key Vault (secrets) · Application Insights and Azure Monitor (observability)
DATA MIGRATION — Azure Data Factory (see the migration workbook)
Team Connect
(SQL / Oracle / blob)
Azure Data Factory
ingest & transform
ADLS / Blob
RAW → CURATED → READY
Azure SQL
iManage staging
iManage
migration waves
Principle: use Azure Data Factory for data pipelines and migration; use Azure Functions and Service Bus for operational application integration.
iManage Integration Module | Technology Solutions | For discussion
5

## Slide 6
DESIGN RATIONALE
Why Azure Data Factory is not the middleware
Data Factory is the right tool for the migration and the wrong tool for the operational integration.
Data Factory is built for
Data movement and ETL / ELT
Batch processing and transformation
Pipeline orchestration on a schedule
Connecting databases, storage and data platforms
Exactly the Team Connect migration workload
The integration needs
Continuous polling and stateful change detection
Idempotent processing and at-least-once delivery
Per-application retry, dead-letter and replay
Independent downstream processing and business logic
New downstream apps added without touching the source
The failure mode:
a Data Factory pipeline that calls Exterro, then TyMetrix, then the next application, gradually absorbs every application's mapping, retry behaviour, error handling and routing. An ETL orchestration service quietly becomes a custom integration platform — one that has to be redesigned every time an application is added.
iManage Integration Module | Technology Solutions | For discussion
6

## Slide 7
RIGHT-SIZING THE PLATFORM
Is this over-engineered?
A fair challenge. The answer is no — but the MVP should be smaller than the target state.
Build now — the MVP
Azure Functions — poller, normalizer, two adapters
Service Bus topic with a subscription per application
Azure SQL for integration state and idempotency
Key Vault for credentials
Application Insights for monitoring and alerting
Defer until it is needed
API Management — only if manual sync from the iManage UI is a day-one requirement
Data Factory, ADLS and staging SQL — provisioned with the platform, built when migration starts
Additional downstream adapters — one Service Bus subscription each, added on demand
Verdict
Not over-engineered. The MVP is five managed services with no servers to run, and it is close to the minimum that supports retry, replay and a second downstream application. The genuine cost here is the environment runway, and that cost is identical for a simple design and a scalable one — so a design that cannot absorb the third and fourth downstream application would mean paying the runway twice. Trim API Management out of the MVP if manual sync can wait; keep the rest.
iManage Integration Module | Technology Solutions | For discussion
7
Notes: If challenged on cost: the alternative designs still need the same IAP, PID, CSP review, CIDR, firewall and ARE deployment. The infrastructure runway does not shrink with a simpler design.

## Slide 8
THE CRITICAL PATH
The Azure environment runway: 2 to 4 months
Gated end to end, and identical whether TD or Kroll writes the code.
1
Submit IAP · Infrastructure Architect assigned
1 day
2
IA and Cloud team produce the PID
1–2 wks
3
Architecture design review of the PID
1–2 wks
4
Cloud CSP review — Cloud, Network, Privacy
3–4 wks
5
Cloud profile and subscription onboarding
1–2 wks
6
CIDR / subnet allocation, per environment
3 days each
7
AD group provisioning for cloud infrastructure
1 wk
8
Firewall requests — PAT and PROD
5-day SLA
9
PAT infrastructure deployment by ARE
5–8 days
10
PROD infrastructure deployment by ARE
5–8 days
11
Key Vault, managed identity, secrets onboarding
1–1.5 wks
12
Environment validation and connectivity proving
1–2 wks
9 – 16 weeks
On plan; 22 weeks is the downside. Starting at week 1 it overlaps design and the build, so 6–10 weeks land on the critical path.
Do this now
Name Data Factory, ADLS/Blob and the Azure SQL staging database in this PID. Adding them after the PID is baselined costs 6–10 weeks of rework.
iManage Integration Module | Technology Solutions | For discussion
8

## Slide 9
WORK BREAKDOWN · 1 OF 3
Steps: design, discovery and environment setup
Identical in both build options. Kroll is engaged as the iManage subject-matter expert throughout Phase A.
Step | Owner | Elapsed | Gate / dependency
PHASE A — DESIGN & DISCOVERY (4–6 weeks) |  |  | 
Confirm integration scope and downstream requirements | TD BA + app teams | 2–3 wks | Project kickoff
iManage API discovery — endpoints, auth, rate limits, change detection | Kroll (SME) + TD | 1.5–3 wks | Kroll SME access
Field-level mapping: iManage → canonical model → Exterro / TyMetrix | TD + Kroll + vendors | 2–3 wks | Scope, API discovery
Solution design: polling, watermark, idempotency, retry, replay | TD Architecture + Kroll | 2–3 wks | API discovery
Architecture review and design sign-off | TD Architecture | 2–3 wks | Solution design
SOW / contract change with Kroll (Kroll option only) | TD Sourcing + Legal | 2–4 wks | Build decision
PHASE B — AZURE ENVIRONMENT SETUP (9–16 weeks · starts at week 1, alongside design) |  |  | 
IAP submission, PID production, architecture review | TD Infra + IA + Cloud | 2–4 wks | Funded project
Cloud CSP security review — Cloud, Network, Privacy teams | Security / Network / Privacy | 3–4 wks | PID issued
Cloud profile onboarding, CIDR allocation, AD group provisioning | Cloud + Network + IAM | 2–4 wks | Reviews passed
Firewall requests and ARE deployment — PAT then PROD | Network + ARE | 3–4 wks | CIDR approved
Key Vault, managed identity, observability, connectivity proving | TD Infrastructure | 2–3 wks | ARE deployment
iManage Integration Module | Technology Solutions | For discussion
9

## Slide 10
WORK BREAKDOWN · 2 OF 3
Steps: code build and vendor handover
Phase C is the only phase the build decision changes. Phase D exists only if Kroll writes the code.
Step | Owner | Elapsed | On critical path?
PHASE C — CODE BUILD (TD 6–8 weeks · Kroll 4–5 weeks · runs in parallel with Phase B) |  |  | 
Repository, CI/CD pipeline and infrastructure-as-code templates | TD Dev (TD-owned either way) | 1.5–2 wks | No
iManage poller: watermark, pagination, throttling, change detection | TD Dev or Kroll | 2–3 wks | No
Canonical matter model, normalizer and validation rules | TD Dev or Kroll | 1.5–2 wks | No
Service Bus topic, subscriptions, dead-letter and retry policy | TD Dev or Kroll | 0.5–1 wk | No
Exterro adapter — mapping, API calls, error handling, retry | TD Dev or Kroll | 1.5–2 wks | No
TyMetrix adapter — mapping, API calls, error handling, retry | TD Dev or Kroll | 1.5–2 wks | No
Integration state store: status, idempotency, correlation, replay | TD Dev or Kroll | 1–1.5 wks | No
Manual 'Sync Matter' API via API Management (deferrable) | TD Dev or Kroll | 1–2 wks | No
Observability instrumentation, dashboards and runbooks | TD Dev | 1–1.5 wks | No
PHASE D — VENDOR CODE HANDOVER (4–6 weeks elapsed · 2–4 on the critical path · Kroll option only) |  |  | 
IP ownership, licensing and source code escrow confirmed | TD Legal + Sourcing | 1–2 wks | Yes
Code transfer into TD repository, secrets externalised to Key Vault | TD Dev | 1.5–2.5 wks | Yes
TD code review, SAST / DAST / SCA scanning and remediation | TD Dev + Security | 2–3 wks | Yes
Third-party code risk assessment and knowledge transfer | TD Risk · Kroll → TD | 2–3 wks | Yes
iManage Integration Module | Technology Solutions | For discussion
10

## Slide 11
WORK BREAKDOWN · 3 OF 3
Steps: deployment, testing and support
TD-owned in both options. This is where a vendor-built module costs an extra round-trip on every defect.
E. Deployment
2–3 wks
Deploy to DEV and PAT through the ARE pipeline with change tickets
Defect fix and redeploy cycles through PAT
PROD deployment with CAB change approval and implementation window
Cutover sequence, initial seed sync, rollback plan and runbook
F. Testing
5–6 wks
Component and integration testing in PAT against real iManage data
End-to-end testing with Exterro and with TyMetrix (vendor coordination)
Resilience: retry, dead-letter, replay, watermark recovery, duplicates
Performance and volume testing, plus security scanning
UAT and business sign-off from legal operations
G. Support & run
4 wks +
Runbooks, alert-to-ticket routing and the on-call model
Support model agreement — TD L1/L2 versus Kroll L3
Four weeks of hypercare after go-live
Steady-state: patching, secret rotation, downstream API version changes
Testing is the second-largest block of added time, and it is unavoidable: two external vendors have to be coordinated for end-to-end validation before the business will sign off.
iManage Integration Module | Technology Solutions | For discussion
11

## Slide 12
DECISION POINT
Who writes the integration code?
Scope of the decision: the application code only. TD owns the infrastructure, the deployment and production support in every scenario.
OPTION 1
TD builds
Development
6–8 weeks — learning curve on the iManage API and on Azure Functions
Handover
None — the code is written inside TD's repository from day one
Supportability
Strong — the team that built it supports and extends it
Main risk
Do we have available developers with Azure Functions and C# experience?
OPTION 2
Kroll builds and hands over
Development
4–5 weeks — Kroll knows the iManage API and has delivered on Azure
Handover
4–6 weeks elapsed, 2–4 on the critical path — IP terms, code transfer, TD code review, scanning, KT
Supportability
Weaker — TD inherits and supports code it did not write
Main risk
The handover gate is serial, and it lands directly on the critical path
The uncomfortable finding:
Kroll's two-week development advantage runs in parallel with the environment runway, so it never reaches the critical path — while the handover it creates does. Choosing Kroll to save time does not save time.
iManage Integration Module | Technology Solutions | For discussion
12
Notes: This is the slide to spend time on. The decision should be made on capability and long-term supportability, not on schedule - because the schedule barely moves.

## Slide 13
SCHEDULE IMPACT
TD build versus Kroll build, phase by phase
Elapsed weeks on the critical path, using planning midpoints. Lower is better.
Chart: Elapsed weeks on the critical path
| Hypercare | Testing & UAT | Deployment | Vendor code handover | Code build (on critical path) | Azure environment | Design & discovery
TD builds the code | 4 | 5.5 | 2.5 | 0 | 0.5 | 8 | 5
Kroll builds and hands over | 4 | 6.5 | 2.5 | 3 | 0 | 8 | 6
TD builds
≈ 21 weeks
5 months
Kroll builds
≈ 26 weeks
6 months
Difference
+ 5 weeks
in Kroll's favour: none
Sensitivity: if TD has no available developers, Option 1 gains 4–8 weeks of ramp-up and the two options converge.
iManage Integration Module | Technology Solutions | For discussion
13

## Slide 14
TOTAL SCHEDULE IMPACT
What this integration adds to the project
17–26
weeks added to go-live
≈ 4 to 6 months if TD writes the code
9–16
weeks of Azure runway
Environment provisioning; 6–10 weeks of it on the critical path
6–8
weeks of development
The only part of the schedule the vendor decision changes
4–6
weeks of handover
Added only if Kroll writes the code — and it is serial
None of this time is in the current project plan. The environment runway starts the day the IAP is submitted — every week that submission waits is a week added to the end date.
14

## Slide 15
RECOMMENDATION
Option 3 — co-development
Kroll's iManage knowledge without the handover gate. This is the proposal for the team to challenge.
Kroll writes the integration code inside TD's repository and CI/CD pipeline, with TD engineers embedded from day one. TD owns the Azure infrastructure, the deployment pipeline, the production release and long-term support.
1
Captures the real gap
TD does not yet know which iManage APIs will be used. That knowledge sits with Kroll, and this gets it into the codebase directly.
2
Deletes the handover gate
No IP transfer, no arm's-length code review cycle, no knowledge-transfer sprint. The code never leaves TD's SDLC — saving 2–4 critical-path weeks.
3
Protects supportability
TD engineers know the code on day one of hypercare, and can add the third and fourth downstream adapter without re-engaging the vendor.
Conditions
At least one TD developer is named to the build from the start — without that, this is just Option 2 with extra steps.
The SOW fixes IP ownership, TD coding standards, test evidence requirements and a defect warranty period up front.
iManage Integration Module | Technology Solutions | For discussion
15

## Slide 16
RISK REGISTER
What could move these numbers
The estimates assume published SLAs are met and no review cycle has to be repeated.
Risk | Impact on the schedule | Likelihood | Mitigation
No TD developers available with Azure Functions and C# experience | Adds 4–8 weeks of ramp-up; flips the build recommendation | High | Confirm named resources before the build decision is made
Cloud CSP review returns material findings | PID rework plus a second review cycle: 3–6 weeks | Medium | Pre-socialise the design with Security, Network and Privacy
No dev or sandbox subscription, so coding cannot run in parallel | The build becomes serial behind the runway: 6–8 weeks | Medium | Request a development subscription in the IAP
iManage API cannot support reliable change detection | Design falls back to full scans or scheduled extracts: 3–6 weeks | Medium | Confirm with Kroll in Phase A, before the design is baselined
Data Factory and staging SQL left out of the initial PID | 6–10 weeks of PID rework and ARE redeployment later | High | Add them to the PID scope now
Queue time beyond published SLAs at network, IAM and ARE gates | Directly extends the runway toward the 5-month worst case | High | Raise every request as early as its dependency allows
TD supports code it did not write (Kroll option) | Longer mean time to repair; vendor dependency for every change | High | Co-development, or a contracted L3 support agreement
iManage Integration Module | Technology Solutions | For discussion
16

## Slide 17
NEXT STEPS
Decisions needed from this meeting
1
Who writes the integration code — TD, Kroll, or co-development?
Drives the SOW, the resourcing plan and the Phase A start date.
Technology leadership
2
Are Data Factory and the staging database in the initial PID?
Worth 6–10 weeks. The window closes when the PID goes to architecture review.
Infrastructure Architect
3
Which TD developers are named, and from what date?
The single largest variable in the estimate.
Engineering manager
4
Is manual sync from the iManage UI day-one or a fast-follow?
Decides whether API Management is in the MVP.
Business + TD BA
5
When is the IAP submitted?
The runway starts on this date. Every week of delay is a week on the end date.
Project manager
Supporting detail: iManage_Integration_Module_Effort_and_Timeline.xlsx · TeamConnect_to_iManage_Migration_Options_and_Effort.xlsx