## Slide 1
TD
TECHNOLOGY SOLUTIONS
iManage Integration Module
Additional technology work, effort and timelines
4 – 6
months added if
TD builds the code
4 – 5.5
months added if
Kroll builds the code
2 – 4
months of environment
setup, either way
Notes: Headline: whoever writes the code, the environment setup dominates and the project still adds four to six months.

## Slide 2
BACKGROUND
Why we need an integration module
None of the three systems can move data on their own.
iManage
Matter system
TD-hosted
integration module
(Azure)
Exterro
TyMetrix
Future downstream apps
poll every 2–5 min
push
iManage
No event triggers and no ability to call outbound APIs. It exposes an endpoint that can be pinged.
Exterro and TyMetrix
Cannot send or request data. Both accept batch intake, but something has to assemble and deliver it.
Result
A TD-hosted integration module is the only way matter data moves between the three systems.
iManage Integration Module | Technology Solutions
2

## Slide 3
TARGET ARCHITECTURE
Recommended Azure platform
Azure Functions and Service Bus for the integration. Data Factory for the Team Connect migration.
INTEGRATION
iManage
Function: poller
every 2–5 min
Functions:
canonical model
Service Bus
matter-events
Exterro adapter
TyMetrix adapter
Future adapters
Supporting services: Azure SQL (per-matter integration state) · Key Vault (secrets) · Application Insights and Azure Monitor (monitoring)
MIGRATION
Team Connect
(SQL / Oracle / blob)
Azure Data Factory
ingest & transform
ADLS / Blob
RAW → CURATED → READY
Azure SQL
iManage staging
iManage
migration waves
Why not Data Factory here
A 2–5 minute poll is ~20,000 pipeline runs a month, most finding nothing, with runs overlapping whenever a downstream is slow. Data Factory retries activities, not records, so per-matter status, retry and replay end up hand-built in SQL.
Why there is no API gateway
API Management was in the vendor's reference design to front a 'Sync Matter' button in the iManage UI. iManage cannot make outbound calls, so nothing calls in. It has been removed from the design, the PID and the security review.
On the Data Factory familiarity point
Data Factory is still the right tool for the Team Connect migration, so that skill stays in use on this project. The gap is Azure Functions and C# capability for the integration.
iManage Integration Module | Technology Solutions
3

## Slide 4
WORK STEPS · 1 OF 2
Design and environment setup
Identical in both build options. Kroll is the iManage subject-matter expert throughout design.
Step | Owner | Elapsed | Gate / dependency
DESIGN AND DISCOVERY (4–6 weeks) |  |  | 
Confirm integration scope and downstream requirements | TD BA + app teams | 2–3 wks | Project kickoff
iManage API discovery: endpoints, auth, rate limits, 'ready' state detection | Kroll (SME) + TD | 1.5–3 wks | Kroll SME access
Field-level mapping: iManage to canonical model to Exterro / TyMetrix | TD + Kroll + vendors | 2–3 wks | Scope, API discovery
Solution design: polling, watermark, idempotency, retry, replay | TD Architecture + Kroll | 2–3 wks | API discovery
Architecture review and design sign-off | TD Architecture | 2–3 wks | Solution design
AZURE ENVIRONMENT SETUP (9–16 weeks · starts at week 1, alongside design and the build) |  |  | 
IAP submission, PID production, architecture review | TD Infra + IA + Cloud | 2–3 wks | Funded project
Cloud CSP security review: Cloud, Network and Privacy teams | Security / Network / Privacy | 3–4 wks | PID issued
Cloud profile onboarding, CIDR allocation, AD group provisioning | Cloud + Network + IAM | 2–3 wks | Reviews passed
Firewall requests and ARE deployment: PAT then PROD | Network + ARE | 3–4 wks | CIDR approved
Key Vault, managed identity, monitoring, connectivity proving | TD Infrastructure | 1–2 wks | ARE deployment
iManage Integration Module | Technology Solutions
4

## Slide 5
WORK STEPS · 2 OF 2
Development, handover, deployment and support
Development is the only phase the build decision changes. Handover applies only if Kroll builds.
Step | Owner | Elapsed | Applies to
CODE DEVELOPMENT (TD 8–10 weeks · Kroll 4–5 weeks · runs in parallel with the environment setup) |  |  | 
Repository, CI/CD pipeline and infrastructure-as-code templates | TD Dev | 1.5–2 wks | TD-owned either way
iManage poller: 2–5 min timer, watermark, throttling, concurrency guard | TD Dev or Kroll | 2–3 wks | Differs by option
Canonical matter model, normalizer and validation rules | TD Dev or Kroll | 1.5–2 wks | Differs by option
Service Bus topic, subscriptions, dead-letter and retry policy | TD Dev or Kroll | 0.5–1 wk | Differs by option
Exterro adapter and TyMetrix adapter: mapping, API calls, retry | TD Dev or Kroll | 3–4 wks | Differs by option
Integration state store: per-matter status, idempotency, replay | TD Dev or Kroll | 1–1.5 wks | Differs by option
Monitoring instrumentation, dashboards and runbooks | TD Dev | 1–1.5 wks | TD-owned either way
HANDOVER TO TD (2–3 weeks · Kroll option only · Kroll has no access to TD systems) |  |  | 
Kroll delivers the source code with build and deployment documentation | Kroll | 0.5–1 wk | Kroll option only
TD code review and security scanning (SAST, SCA, licence) | TD Dev + Security | 1–1.5 wks | Kroll option only
Reconfigure for the TD environment: config, secrets to Key Vault, pipeline | TD Dev | 1–1.5 wks | Kroll option only
Knowledge transfer, with Kroll available to consult | Kroll to TD | 1–1.5 wks | Kroll option only
DEPLOYMENT, TESTING AND SUPPORT (7–9 weeks to go-live, plus 4 weeks hypercare · TD-owned in both options) |  |  | 
Deploy to PAT and PROD through ARE, with CAB approval and cutover | TD Dev + ARE | 2–3 wks | Both options
Testing: component, end-to-end with Exterro and TyMetrix, resilience, security | TD QA + vendors | 4–5 wks | Both options
UAT and business sign-off | Business + TD | 2 wks | Both options
Hypercare, runbooks and transition to the run team (after go-live) | TD Dev + Run team | 4 wks | Both options
iManage Integration Module | Technology Solutions
5

## Slide 6
ENVIRONMENT SETUP
Azure environment: 2 to 4 months
This is the same whoever writes the code, and it is the largest single block of added time.
1
Submit IAP · Infrastructure Architect assigned
1 day
2
IA and Cloud team produce the PID
1–2 wks
3
Architecture design review of the PID
1–2 wks
4
Cloud CSP review: Cloud, Network, Privacy
3–4 wks
5
Cloud profile and subscription onboarding
1–2 wks
6
CIDR / subnet allocation, per environment
3 days each
7
AD group provisioning for cloud infrastructure
1 wk
8
Firewall requests: PAT and PROD
5-day SLA
9
PAT infrastructure deployment by ARE
5–8 days
10
PROD infrastructure deployment by ARE
5–8 days
11
Key Vault, managed identity, secrets onboarding
1–1.5 wks
12
Environment validation and connectivity proving
1–2 wks
9 – 16 weeks
On plan, with 22 weeks as the downside if a review repeats. DEV, PAT and PROD each repeat the addressing, firewall and deployment steps.
Include the migration services in this PID
Data Factory, ADLS/Blob and the Azure SQL staging database. Adding them after the PID is baselined costs 6–10 weeks of rework.
iManage Integration Module | Technology Solutions
6

## Slide 7
DECISION
Who writes the integration code
This covers the application code only. TD owns the environment, deployment, configuration and support in both options.
OPTION 1
TD builds
Development
8–10 weeks. No one on the current team has built this, so there is ramp-up on the iManage API and the Azure services, with Kroll consulting.
Handover
None. The code is written in TD's environment from the start.
Support
TD supports and extends code it wrote.
Main risk
This is the least certain estimate in the plan, because there is no prior build to base it on.
OPTION 2
Kroll builds
Development
4–5 weeks. Kroll has built this integration before and already knows the iManage API.
Handover
2–3 weeks. Kroll builds in their own environment and delivers the source; TD reviews, scans, reconfigures and deploys it here.
Support
TD supports code it did not write, with Kroll available to consult.
Main risk
TD has no visibility of the build while it happens, so standards and test evidence have to be specified up front.
Everything except development is the same in both options.
Kroll saves 4–5 weeks of build time and removes the ramp-up risk. The environment setup, deployment, testing and support are TD-owned and unchanged, so the project still adds four to five and a half months.
iManage Integration Module | Technology Solutions
7
Notes: Kroll cannot build inside TD systems - no access. They build in their own environment and deliver source code that TD reviews, reconfigures and deploys.

## Slide 8
TIMELINE
Where the time goes
Elapsed weeks per phase. Phases overlap, so the totals are less than the sum of the bars.
Chart: Elapsed weeks
| Testing & UAT | Deployment | Handover to TD | Code development | Azure environment setup | Design & discovery
TD builds the code | 5.5 | 2.5 | 0 | 9 | 12.5 | 5
Kroll builds the code | 5.5 | 2.5 | 2.5 | 4.5 | 12.5 | 5
19–26 weeks
added to go-live if TD builds the code (4.5 – 6 months)
17–24 weeks
added to go-live if Kroll builds the code (4 – 5.5 months)
9–16 weeks
environment setup, identical in both options
The point
Kroll saves 4–5 weeks on development. The environment setup, deployment, testing and support do not change, so significant time is added to the project either way.
iManage Integration Module | Technology Solutions
8

## Slide 9
SUMMARY
Recommendations
Five decisions, side by side. Step-level detail and timings are in the supporting workbook.
Topic | Recommendation | Why | Cost of not doing it
Integration platform | Azure Functions + Service Bus, not Data Factory | A 2–5 minute poll with per-matter 'ready' flags needs per-record retry, dead-letter and replay. Data Factory retries activities, not records. | ~20,000 pipeline runs a month, plus failure tracking and replay maintained in SQL by TD.
Who writes the code | Kroll builds it and delivers the source; TD reviews, reconfigures and deploys | Kroll has built this before and knows the iManage API. No one on the current TD team has, so TD carries 8–10 weeks and the least certain estimate in the plan. | 4–5 extra weeks of development, and ramp-up risk on top.
Infrastructure and support | TD owns the Azure environment, deployment, configuration and production support | Kroll has no access to TD systems. They build in their own environment and hand over source code. | Not applicable — this holds in every option.
Ongoing support | Agree Kroll consulting availability for L3 after handover | TD will be supporting and extending code it did not write, and adding downstream adapters later. | Longer time to repair and a vendor dependency for every future change.
Migration staging | Name Data Factory, ADLS/Blob and Azure SQL staging in the initial PID | They are then provisioned in the same ARE deployment as the integration platform. | 6–10 weeks of PID rework, a second security review and an ARE redeployment.
Decisions needed today: who writes the code · are the migration services in the PID · which TD developers are named · when is the IAP submitted
iManage Integration Module | Technology Solutions
9