## 1. Summary
iManage Integration Module ¦ Additional Work, Effort and Timeline
Middleware integration: iManage → Exterro / TyMetrix. TD builds the code vs. Kroll builds the code.
HEADLINE NUMBERS
Added time to go-live — TD builds | 19 – 26 weeks |  | ≈ 4.5 – 6 months
Added time to go-live — Kroll builds | 17 – 24 weeks |  | ≈ 4 – 5.5 months
Azure environment setup | 9 – 16 weeks |  | 2 – 4 months. Identical in both options and the largest single block.
Development saving if Kroll builds | 4 – 5 weeks |  | Kroll has built this before. Partly offset by 2 – 3 weeks of handover.
Phase | Scope | TD builds (elapsed weeks) | Kroll builds (elapsed weeks) | Difference | Comment
Design and discovery | Requirements, iManage API discovery, field mapping, solution design, architecture sign-off | 4 – 6 | 4 – 6 | None | Same work either way. Kroll is the iManage subject-matter expert in both options.
Azure environment setup | IAP, PID, architecture review, Cloud CSP review, CIDR, AD groups, firewall, ARE deployment | 9 – 16 | 9 – 16 | None | Kroll building in their own Azure tenancy removes none of these gates. TD owns the environment either way.
Code development | Poller, canonical matter model, Service Bus, Exterro and TyMetrix adapters, state store | 8 – 10 | 4 – 5 | Kroll saves 4 – 5 wks | Kroll has built this integration before and knows the iManage API. No one on the current TD team has, so TD carries ramp-up and the least certain estimate here.
Handover to TD | Source code delivered, TD code review and security scan, reconfigure for the TD environment, knowledge transfer | Not applicable | 2 – 3 | Kroll costs 2 – 3 wks | Kroll has no access to TD systems, so they build in their own environment and hand over source code that TD redeploys and reconfigures.
Deployment | PAT and PROD deployment through ARE, CAB approval, cutover | 2 – 3 | 2 – 3 | None | TD deploys in both options.
Testing and UAT | Component, end-to-end with Exterro and TyMetrix, resilience, performance, security, UAT | 5 – 6 | 5 – 6 | None | TD-led in both options.
Hypercare | Runbooks, on-call model, four weeks of elevated support after go-live | 4 | 4 | None | Sits after go-live and is excluded from the totals below.
ADDED TIME TO GO-LIVE |  | 19 – 26 wks (4.5 – 6 months) | 17 – 24 wks (4 – 5.5 months) | Kroll ≈ 2 wks earlier | Development is the only phase that changes.
WHAT THIS COMES DOWN TO
Everything except code development is the same in both options. The environment, deployment, testing and support are TD-owned and take
the same time whoever writes the code, so the build decision only moves development.
Kroll is faster because they have built this integration before and know the iManage API. TD would be building it for the first time with
Kroll consulting, which is slower and carries more estimating risk.
Kroll cannot build inside TD systems — they have no access. They build in their own environment and deliver source code that TD reviews,
reconfigures and deploys here. That handover is the 2–3 weeks above, and Kroll stays available to consult through it.
Either way the project adds four to six months, and the environment setup is the reason.

## 2. Work Steps
Complete Work Breakdown
Every step required to design, build, deploy, test and support the iManage → Exterro / TyMetrix integration
ID | Work Step | What It Involves | Owner | Effort (person-days) | Elapsed Low (wks) | Elapsed High (wks) | Dependency | Applies To
DESIGN AND DISCOVERY · 4–6 weeks · same in both options; Kroll is the iManage subject-matter expert throughout
A1 | Confirm integration scope and downstream requirements | Which matter attributes Exterro and TyMetrix need, sync frequency, volumes, direction of flow | TD BA + app teams | 10 | 2 | 3 | Project kickoff | Both
A2 | iManage API discovery | Usable endpoints, authentication, rate limits, pagination, and how the 'ready' state change is detected on a 2–5 minute poll | Kroll (SME) + TD | 10 | 1.5 | 3 | Kroll SME access | Both
A3 | Field-level data mapping | iManage to canonical matter model to the Exterro and TyMetrix contracts, including reference and code values | TD + Kroll + vendors | 15 | 2 | 3 | A1, A2 | Both
A4 | Integration solution design | Polling strategy and watermark, idempotency, retry, dead-letter, replay, correlation IDs, error classification | TD Architecture + Kroll | 15 | 2 | 3 | A2 | Both
A5 | Non-functional requirements | Volumes and throughput, sync SLA, availability, DR, data retention, logging and audit | TD Architecture | 5 | 1 | 1 | A1 | Both
A6 | Architecture review and design sign-off | Formal review of the integration pattern and the Azure service selection | TD Architecture | 5 | 2 | 3 | A4 | Both
AZURE ENVIRONMENT SETUP · 9–16 weeks · identical in both options; starts at week 1, alongside design and the build
B1 | Submit IAP; Infrastructure Architect assigned | Raise the infrastructure assessment request against the project | TD Infrastructure | 1 | 0.2 | 0.2 | Funded project | Both
B2 | IA and Cloud team produce the PID | Infrastructure design covering subscription, network, resources, data flows and security controls | Infra Architect + Cloud | 10 | 1 | 2 | B1 | Both
B3 | Architecture design review of the PID | Formal architecture governance review and approval of the target Azure design | TD Architecture | 5 | 1 | 2 | B2 | Both
B4 | Cloud CSP security review | Joint review with Cloud, Network and Privacy; data classification, egress paths, control mapping and remediation | Security / Network / Privacy | 15 | 3 | 4 | B2 | Both
B5 | Cloud profile and subscription onboarding | Subscription, management group placement, policy assignment, tagging and cost centre | Cloud onboarding | 5 | 1 | 2 | B3, B4 | Both
B6 | CIDR / subnet allocation | 3 business days plus review, repeated for DEV, PAT and PROD | Network | 9 | 1.8 | 3 | B5 | Both
B7 | AD group provisioning | Access groups for the platform and each environment, plus RBAC role mapping | IAM | 5 | 1 | 1.5 | B5 | Both
B8 | Firewall requests for PAT and PROD | Rules to iManage, Exterro, TyMetrix and internal endpoints, 5 business day SLA each | Network | 10 | 1 | 1.5 | B6 | Both
B9 | PAT infrastructure deployment by ARE | Resources, network security groups, private endpoints and change tickets, 5–8 business days | ARE | 8 | 1 | 1.6 | B6, B8 | Both
B10 | PROD infrastructure deployment by ARE | Resources, network security groups, private endpoints and change tickets, 5–8 business days | ARE | 8 | 1 | 1.6 | B6, B8 | Both
B11 | Key Vault, managed identity and secrets onboarding | Vault creation, access policies, managed identity, credential load and rotation process | TD Infrastructure | 5 | 1 | 1.5 | B9 | Both
B12 | Monitoring onboarding | Application Insights and Azure Monitor workspaces, log retention, alert routing to the run team | TD Infrastructure | 5 | 1 | 1.5 | B9 | Both
B13 | Environment validation and connectivity proving | Prove network paths and authentication to iManage, Exterro and TyMetrix from PAT and PROD | TD Infrastructure + Dev | 5 | 1 | 2 | B9, B10 | Both
CODE DEVELOPMENT · TD 8–10 weeks / Kroll 4–5 weeks · the only phase that changes with the build decision
C1 | Repository, CI/CD pipeline and infrastructure-as-code | Repo and branching standards, build and release pipeline, Bicep or Terraform templates, quality gates | TD Dev | 10 | 1.5 | 2 | B5 | TD-owned either way
C2 | iManage poller | Timer trigger every 2–5 minutes, durable watermark, pagination, throttling, concurrency guard, change and delete detection | TD Dev or Kroll | 15 | 2 | 3 | A4, C1 | Differs
C3 | Canonical matter model and normalizer | Mapping iManage records to the internal matter model, with required-field validation and business rules | TD Dev or Kroll | 10 | 1.5 | 2 | A3 | Differs
C4 | Service Bus topic, subscriptions and dead-letter handling | matter-events topic, a subscription per downstream system, retry policy, DLQ and replay tooling | TD Dev or Kroll | 5 | 0.6 | 1 | A4 | Differs
C5 | Exterro adapter | Canonical to Exterro mapping, API calls, Exterro-specific error handling, transient retry, status recording | TD Dev or Kroll | 10 | 1.5 | 2 | A3, C3 | Differs
C6 | TyMetrix adapter | Canonical to TyMetrix mapping, API calls, TyMetrix-specific error handling, transient retry, status recording | TD Dev or Kroll | 10 | 1.5 | 2 | A3, C3 | Differs
C7 | Integration state store | Azure SQL schema for per-matter status, idempotency keys, correlation IDs, retry counts and replay | TD Dev or Kroll | 8 | 1 | 1.5 | A4 | Differs
C8 | Monitoring instrumentation and runbooks | Custom telemetry, end-to-end correlation, dashboards, alert thresholds and operational runbooks | TD Dev | 8 | 1 | 1.5 | B12 | TD-owned either way
C9 | Unit tests and pipeline security gates | Unit and component tests, SAST, SCA and open-source scanning, code coverage thresholds | TD Dev or Kroll | 8 | 1 | 1.5 | C1 | Differs
HANDOVER TO TD · 2–3 weeks · Kroll option only; Kroll has no access to TD systems
D1 | Kroll delivers the source code | Source, configuration templates, build and deployment documentation, and test evidence | Kroll | 5 | 0.5 | 1 | Code complete | Kroll option
D2 | TD code review and security scanning | Peer review against TD coding standards plus SAST, DAST, SCA and licence scanning, with remediation | TD Dev + Security | 10 | 1 | 1.5 | D1 | Kroll option
D3 | Reconfigure for the TD environment | Load into TD SCM, externalise configuration and secrets to Key Vault, align to TD IaC and the ARE pipeline | TD Dev | 8 | 1 | 1.5 | D2 | Kroll option
D4 | Knowledge transfer | Walkthroughs so TD developers and the run team can operate, patch and extend the code, with Kroll consulting | Kroll to TD | 8 | 1 | 1.5 | D2 | Kroll option
DEPLOYMENT · 2–3 weeks · TD-owned in both options
E1 | Deploy to DEV and PAT through the ARE pipeline | Release build, per-environment configuration, change tickets and deployment verification | TD Dev + ARE | 5 | 1 | 2 | B9, code complete | Both
E2 | Defect fix and redeploy cycles | Iterations through PAT as integration and end-to-end defects are found and fixed | TD Dev (or Kroll) | 8 | 1 | 2 | E1, F1 | Both
E3 | PROD deployment and CAB change approval | Production release package, change record, CAB approval and implementation window | TD Dev + ARE | 5 | 1 | 1.5 | B10, F5 | Both
E4 | Cutover, rollback plan and runbook | Go-live sequence, initial seed sync, rollback procedure and support handover pack | TD Dev + Run team | 5 | 0.5 | 1 | E3 | Both
TESTING · 5–6 weeks · TD-led in both options
F1 | Component and integration testing in PAT | Poller, normalizer, Service Bus routing and adapters tested against real iManage PAT data | TD QA + Dev | 10 | 2 | 3 | E1 | Both
F2 | End-to-end testing with Exterro and TyMetrix | Full matter lifecycle through to both systems, with vendor coordination and test data alignment | TD QA + vendors | 20 | 2 | 3 | F1 | Both
F3 | Resilience testing | Retry, dead-letter, replay, watermark recovery, duplicate suppression and downstream outage simulation | TD QA + Dev | 5 | 1 | 2 | F1 | Both
F4 | Performance and security testing | Poll cadence under peak volume, API throttling behaviour, vulnerability scanning and secrets handling review | TD QA + Security | 10 | 2 | 3 | F1 | Both
F5 | UAT and business sign-off | Legal operations validate matter data in Exterro and TyMetrix, and approve go-live | Business + TD | 10 | 2 | 2 | F2 | Both
SUPPORT AND TRANSITION TO RUN · 4 weeks after go-live
G1 | Runbooks, alert routing and on-call model | Operational documentation, monitoring thresholds, escalation paths and support rota | TD Run team | 5 | 1 | 2 | C8, E4 | Both
G2 | Support model agreement | Who fixes what: TD L1/L2 versus Kroll L3 consulting for the integration code | TD + Kroll | 3 | 1 | 2 | Build decision | Both
G3 | Hypercare | Elevated support after go-live: daily monitoring, rapid defect turnaround, tuning of poll and retry settings | TD Dev + Run team | 20 | 4 | 4 | E4 | Both
G4 | Steady-state ownership | Patching, secret and certificate rotation, downstream API version changes, capacity and cost management | TD Run team | Ongoing | — | — | G3 | Both
| TIME TO GO-LIVE — TD builds the code |  |  | ≈ 335 pd | 19 wks | 26 wks | ≈ 4.5 – 6 months
| TIME TO GO-LIVE — Kroll builds the code |  |  | ≈ 315 pd | 17 wks | 24 wks | ≈ 4 – 5.5 months
NOTE
Effort in person-days is work content. Elapsed weeks is calendar time including reviews, approvals and queueing.
Phase totals are less than the sum of their steps because steps within a phase overlap, and the environment setup runs from week 1
alongside design and the build. Hypercare follows go-live and is excluded from the totals.

## 3. Azure Environment Setup
Azure Environment Setup
9 to 16 weeks, identical whether TD or Kroll writes the code. Starts at IAP submission in week 1, alongside design and the build.
Seq | Gate / Activity | Accountable Team | SLA / Duration | Elapsed Low (wks) | Elapsed High (wks) | What Blocks If This Slips | Repeats Per Environment?
1 | Submit IAP request; Infrastructure Architect assigned | TD Infrastructure | 1 business day | 0.2 | 0.2 | Nothing starts — this is the entry gate | No
2 | IA and Cloud team produce the PID | Infra Architect + Cloud | 1 – 2 weeks | 1 | 2 | No design means no security review and no build request | No
3 | Architecture design review of the PID | TD Architecture | 1 – 2 weeks | 1 | 2 | PID cannot be baselined; downstream requests are rejected | No
4 | Cloud CSP security review | Security / Network / Privacy | 3 – 4 weeks | 3 | 4 | Highest-variance gate. Findings force PID rework and a re-review. | No
5 | Cloud profile and subscription onboarding | Cloud onboarding | 1 – 2 weeks | 1 | 2 | No subscription means no resources can be created | No
6 | CIDR / subnet allocation | Network | 3 business days + review | 0.6 | 1 | No addressing means no NSGs, no private endpoints, no deployment | Yes — DEV, PAT, PROD
7 | AD group provisioning | IAM | 1 week | 1 | 1.5 | The team cannot access the environment they are waiting on | Partly — per environment role
8 | Firewall requests, PAT and PROD | Network | 5 business day SLA | 1 | 1.5 | No connectivity to iManage, Exterro or TyMetrix | Yes — PAT and PROD
9 | PAT infrastructure deployment by ARE | ARE | 5 – 8 business days | 1 | 1.6 | No test environment, so all testing stops | Yes
10 | PROD infrastructure deployment by ARE | ARE | 5 – 8 business days | 1 | 1.6 | No production target, so go-live cannot happen | Yes
11 | Key Vault, managed identity, RBAC and secrets | TD Infrastructure | 1 – 1.5 weeks | 1 | 1.5 | Credentials cannot be stored or rotated to standard | Yes
12 | Environment validation and connectivity proving | TD Infrastructure + Dev | 1 – 2 weeks | 1 | 2 | Integration testing cannot begin | Yes
| TOTAL, WITH NORMAL PARALLELISM |  |  | 9 wks | 16 wks | 2 – 4 months on plan; 5 months worst case
WHY THIS IS THE LARGEST BLOCK OF ADDED TIME
The sequence is gated end to end: IAP, architecture review, cloud profile, CIDR approval, firewall, then ARE provisioning.
Each gate has its own queue, and a finding at the Cloud CSP review sends the PID back to the start of the design loop.
DEV, PAT and PROD each repeat the addressing, firewall and deployment steps.
Submit the IAP in week 1 so this runs alongside design and the code build. That overlap is what keeps the project at 4–6 months.
Include Azure Data Factory, ADLS/Blob and the Azure SQL staging database in this PID. Adding them afterwards costs 6–10 weeks of
rework — see the Team Connect migration workbook.

## 4. Assumptions & Risks
Assumptions, Risks and Open Decisions
# | Assumption / Risk | Impact if it does not hold | Likelihood | Mitigation / Owner
ASSUMPTIONS
1 | The iManage API supports a 'changed since' or state query and can take a 2–5 minute poll | No polling-based change detection; fallback to full scans or scheduled extracts, adding 3–6 weeks | Medium | Confirm with Kroll in design, before the solution is baselined — TD Architecture
2 | Exterro and TyMetrix expose write APIs suitable for per-matter updates | Adapter design changes and vendor engagement; add 2–4 weeks per downstream system | Medium | Obtain both API specifications during design — TD BA
3 | The IAP goes in at week 1 and a dev or sandbox subscription is available | Design and coding become serial behind the environment and the total rises to 8–10 months | Medium | Submit the IAP at project start and request a dev subscription in it — TD Infrastructure
4 | Published SLAs are met with no queue time beyond them at the network, IAM and ARE gates | Every week of queue time is a week of project slip | High | Raise every request as early as its dependency allows — project manager
5 | The Cloud CSP review passes with no material findings | PID rework plus a second review cycle adds 3–6 weeks | Medium | Pre-socialise the design with Security, Network and Privacy before formal submission
6 | Matters are marked 'ready' in the iManage UI and that state is visible to the poller | The trigger mechanism has to be redesigned, changing the poller and the state model | Low | Confirm the field and its lifecycle with Kroll during design — TD BA
RISKS
7 | This integration work is not in the approved project plan or budget | Funding and resourcing decisions become a schedule dependency | High | Take the estimate to the steering committee at the next checkpoint — project sponsor
8 | TD builds it with no prior experience of this integration | The 8–10 week development estimate is the least certain figure here and could run longer | High | Use Kroll to build, with TD reviewing design and code at agreed checkpoints
9 | TD supports and extends code it did not write | Longer time to repair, and a Kroll dependency for defects and future downstream applications | Medium | Protect the handover time and agree Kroll L3 consulting availability up front
10 | No TD developer with Azure Functions and C# experience is available | The TD-build option gains 4–8 weeks of ramp-up and becomes clearly the slower path | High | Confirm named resources before the build decision — engineering manager
11 | Kroll builds without visibility from TD | Coding standards, test evidence and documentation may not meet TD expectations, extending the review | Medium | Specify standards, test evidence and documentation as delivery criteria before the build starts
12 | The 'ready' state is not cleared after a matter is sent | The same matter re-sends on every poll, or the state store has to track sent matters indefinitely | Medium | Agree the write-back or state-clearing mechanism with Kroll during design
13 | Data Factory and the staging database are left out of the initial PID | 6–10 weeks of PID rework and ARE redeployment later | High | Add them to the PID scope now — Infrastructure Architect
14 | Scope grows as more downstream applications are added after go-live | Each new application is a new adapter and subscription — modest if the canonical model holds | Medium | Hold the canonical matter model and adapter pattern; no point-to-point shortcuts
DECISIONS NEEDED
1. Who writes the integration code — TD or Kroll?
2. Are Data Factory and the staging database in the initial PID?
3. Which TD developers are named, and from what date?
4. What are Kroll's delivery criteria: coding standards, test evidence, documentation?
5. When is the IAP submitted?