## Slide 1
TD BANK GROUP · TECHNOLOGY DELIVERY
USFF × EMS · Pipeline · SPID
Consolidation Delivery Options
& Recommendation
What we can realistically deliver by the September commitment — scope, risks and timelines for three delivery options
Executive Leadership Review
July 2026 | Confidential — TD Bank internal use only

## Slide 2
EXECUTIVE SUMMARY
The ask: confirm what we ship by end of September
USFF (Unified Storefront) is absorbing GTS's EMS, Pipeline and SPID tools so GTS users get one front door — non-GTS users keep today's experience unchanged.
The original plan assumed all five EMS flows by end of September. We have already level-set with stakeholders: only the Vendor Expense flow is achievable in that window.
July deep-dives with the PowerApps developers revealed the true scale: 50+ SharePoint lists behind EMS/Pipeline/SPID, undocumented role and permission logic, and a data schema that does not map 1:1 to USFF.
There are no formal requirements. Flows and business logic are being reconstructed from demos, screenshots and the retiring PowerApps — every build decision carries discovery risk.
Data migration is the single largest swing factor: our consolidated master form means a new schema, so legacy data must be transformed, adding a month or more to any option that includes it.
This deck presents three delivery options with pros, cons, risks and timelines, and our recommendation from a technology-delivery perspective.
50+
SharePoint lists behind EMS / Pipeline / SPID — most need schema transformation
0
formal requirements documents — logic reverse-engineered from demos & PowerApps
2
developers remaining after August — capacity constrains every option
Sep 26
committed delivery window — last week of September 2026
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
2

## Slide 3
THE LANDSCAPE
Three applications, one canonical flow — and one gap
STEP 1 · INTAKE
EMS (Intake front door)
GTS SharePoint portal + PowerApp intake. Five expense types. Users triage and submit requests here today.
→
STEP 2 · GO-AHEAD
Pipeline
Strategic go-ahead approval for 3rd-party spend > $100K, submitted ≥ 90 days ahead. Multi-level, agenda-driven approvals run by BOM leads.
→
STEP 3 · EXECUTION
SPID (Signing Party)
Contract-execution approval PowerApp. Depends on an approved Pipeline and an approved Ariba Sourcing Request before it should start.
The five EMS expense types — only Vendor Expense is in scope for September
Vendor Expense
SOWs, GD contracts, licences, renewals — the only type touching procurement / Ariba / USFF today
Approval to Hire
Employee, contractor, contingent, GD staff-aug
Project Request
ATS, ATP and extensions
Other Approvals
Travel, education, control exceptions
Invoice Submission
Ariba or manual (non-Ariba) invoices
!
The gap: no written requirements exist for any of these flows. Everything is being reconstructed from demos, PowerApps logic and 50+ SharePoint lists — the July sessions with the developer team materially expanded known scope.
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
3

## Slide 4
DELIVERY OPTIONS
Three options — scope, timeline and confidence at a glance
 | OPTION 1 — RECOMMENDED Triage + Pipeline for Vendor Expense | OPTION 2 Option 1 + SPID for Vendor Expense | OPTION 3 Full consolidation — all 5 flows
Scope | EMS triage in USFF for Vendor Expense; other 4 types route to existing portals. Pipeline (VE) absorbed into one master USFF form. SPID stays in PowerApp. | Everything in Option 1, plus SPID captured in USFF for Vendor Expense as a standalone intake (net-new questions only, discrepancy checks). | All 5 expense types, both Pipeline types and all SPID flows in USFF. Legacy EMS / Pipeline / SPID retired. Downstream / batch processes excluded.
Data migration | None at launch — in-flight requests finish in legacy apps (parallel run). Optional migration afterwards: +1 month. | Much larger — SPID field volume requires heavy schema transformation. Including it pushes delivery to end of CY2026. | Mandatory — full migration of 50+ SharePoint lists with schema transformation. Longest single work item.
Target date | Last week of September 2026 (with migration: end of October) | Early Q1 FY27 (Oct–Nov 2026) (with migration: end of CY2026) | ~ March 2027 (migration included — not optional)
Change impact | Low–moderate. Non-GTS users see no change; GTS learns one new front door while legacy SPID continues as-is. | High. Split experience — GTS uses USFF for vendor-expense SPID but the legacy portal for all other SPIDs. Significant training effort. | Very high. Every GTS process changes at once; all user groups retrained; downstream teams must adapt to new hand-offs.
Key dependency | BOM Agenda Builder role logic (being reverse-engineered from PowerApps). | Ariba API for Sourcing Request approval status — setup lead time + vendor rate limits; no UiPath resource for the fallback. | Requirements that do not exist yet, plus downstream / batch process specs (+1 month of discovery minimum).
Delivery confidence | HIGH — prototypes built and validated; scope fits capacity | MEDIUM — hinges on Ariba integration and SPID schema work | LOW — unknown requirements, mandatory migration, 2 devs after August
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
4

## Slide 5
OPTION 1 — RECOMMENDED
Integrated EMS triage + Pipeline for Vendor Expense — no SPID
TARGET DELIVERY
Last week of September 2026
WITH DATA MIGRATION (OPTIONAL ADD-ON)
End of October 2026 (+1 month)
DELIVERY CONFIDENCE
HIGH — prototypes already validated
≡
Scope — what ships
EMS triage runs inside USFF for Vendor Expense; the other four expense types route users to the existing portals from our front door.
Pipeline intake for Vendor Expense is absorbed into USFF.
One master intake form: Pipeline / GTS fields unlock only when the user's answers require them — non-GTS users see no change to today's flow.
SPID remains in the existing PowerApp, linked from USFF.
No data migration at launch: in-flight requests complete in legacy EMS / Pipeline while new requests start in USFF.
✓
Pros
The only option that realistically meets the committed September date.
Front-end prototypes are already built and demo-validated — the highest-risk UX decisions are de-risked.
Minimal disruption to the existing USFF user base; logic-gated fields keep the form familiar.
Removes duplicate intake + Pipeline entry for the highest-volume flow (Vendor Expense).
Establishes the foundation — master form, roles, statuses, agenda model — that Options 2 and 3 build on.
!
Risks & watch-outs
BOM Agenda Builder role logic is still undefined: we are reverse-engineering PowerApps permissioning, and segment / business-unit scoping for BOM leads must be designed as logic-based mapping, not AD-group sprawl.
Access management: the mapping we received is an expense-policy view — translating it into a concise set of AD groups is unresolved.
Parallel run: legacy EMS / Pipeline stay live for in-flight items, so two sources of truth exist until migration.
Change management: GTS users learn a new front door while legacy processes continue alongside.
Adding migration as a standalone feature costs ~1 month (end of October).
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
5

## Slide 6
OPTION 2
Option 1 + SPID for Vendor Expense
TARGET DELIVERY
Early Q1 FY27 (Oct – Nov 2026)
WITH DATA MIGRATION
End of CY2026
DELIVERY CONFIDENCE
MEDIUM — hinges on Ariba + schema work
≡
Scope — what ships
Everything in Option 1, plus the SPID (Signing Party) process captured in USFF for Vendor Expense.
SPID becomes a standalone intake in USFF that asks only net-new questions — no re-entry of data already captured in the master form.
Automatic discrepancy checks flag conflicts between the SPID answers and the original intake / Pipeline record.
Requires pulling approved Sourcing Request status from Ariba via API to gate SPID submission.
✓
Pros
The full vendor-expense lifecycle — intake → Pipeline → SPID — lives in one application.
Zero redundant data entry; discrepancy highlighting improves data quality at the point of capture.
Highest per-flow value: Vendor Expense is the only expense type touching procurement / Ariba / the USFF storefront.
Positions the platform for full consolidation with the schema and integrations already proven.
!
Risks & watch-outs
Split user experience: GTS uses USFF for vendor-expense SPIDs but the legacy portal for ATH and every other SPID — real confusion risk and a significant training load.
Ariba API: setup lead time is material, and Ariba's API rate limits conflict with our Azure pipeline usage.
Fallback (UiPath capturing approval emails) needs a new automation feature — and we have no UiPath resource to build it.
Without SR validation, users could enter any SR number, letting SPIDs through before the sourcing request is actually approved.
SPID data migration is far larger (field volume + schema transformation) — including it pushes delivery to end of year.
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
6

## Slide 7
OPTION 3
Full consolidation — all five flows, EMS + Pipeline + SPID
TARGET DELIVERY
~ March 2027
DATA MIGRATION
Mandatory — 50+ lists, full transform
DELIVERY CONFIDENCE
LOW — requirements & capacity gaps
≡
Scope — what ships
All five EMS expense types, both Pipeline types and every SPID flow consolidated into USFF.
Legacy EMS, Pipeline and SPID applications retired; USFF becomes the single source of truth.
Excludes downstream / batch processes (onboarding portal, invoicing portal, GD Hub, shared data lake) — their requirements and logic are unknown today.
Mandatory full data migration with schema transformation across 50+ SharePoint lists.
✓
Pros
One front door for everything — no parallel apps, no split processes, no routing users between tools.
Single source of truth: dramatically easier to locate, manage, report on and audit request data.
Ends duplicate maintenance, SharePoint permissioning workarounds and swivel-chair overhead for good.
!
Risks & watch-outs
No requirements exist beyond Vendor Expense and Approval to Hire — everything else must be gathered through demos, questions and assumptions. This is the single hardest problem in the programme.
Downstream / batch integration is unscoped: at least +1 month of requirements gathering before build can even be sized.
Mandatory migration of 50+ SharePoint lists into a new schema — the largest, riskiest work item across all options.
The team drops to 2 developers after August — capacity does not match this scope.
Opportunity cost: ARP automation, the Gen-AI model and new business-requested USFF features are deferred for roughly two quarters.
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
7

## Slide 8
RISK BUBBLE
Six risks leadership should see — whatever option we pick
Requirements gap
CRITICAL
No written requirements for any flow. Logic is reverse-engineered from demos and the retiring PowerApps; the July developer sessions grew known scope to 50+ SharePoint lists.
Mitigation: Time-box discovery per flow; lock scope at each phase gate; formal ask to the business for policy docs & reference tables.
Data migration
CRITICAL
One master form = a new schema. Legacy data across EMS / Pipeline / SPID must be transformed, not copied. Today there are multiple sources of truth.
Mitigation: Decouple migration from launch (parallel run); migrate flow-by-flow after cutover; +1 month per major flow.
Access & role management
HIGH
Role mapping received is an expense-policy view, not an app model. BOM leads need segment / BU-scoped visibility; naive AD-group design creates unmanageable sprawl.
Mitigation: One concise AD group per role + logic-based scoping in-app (matrix maintained by EMS team & segment leads).
Change management
HIGH
New USFF processes run beside legacy ones — e.g. USFF for vendor-expense SPID but the old portal for approval-to-hire SPIDs. Users must know which door to use.
Mitigation: In-app routing from USFF to legacy portals; targeted GTS training & comms plan per phase; floor support at each cutover.
Ariba SR validation (Option 2+)
HIGH
SPID depends on an approved Sourcing Request. Ariba API setup takes time and its rate limits conflict with our Azure pipeline; the UiPath email fallback has no resource to build it.
Mitigation: Start Ariba API engagement now (longest lead item); interim manual evidence upload with audit check.
Resource capacity
HIGH
Team drops to 2 developers after August while USFF business asks (ARP automation, Gen-AI model, new features) continue to queue behind this programme.
Mitigation: Leadership decision on backfill; strict phase scope so the 2-dev team is never carrying migration + new build at once.
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
8

## Slide 9
TIMELINES
What each option means for the calendar
Aug
Sep
Oct
Nov
Dec
Jan '27
Feb
Mar
OPTION 1
Triage + Pipeline (VE)
+ migration → end Oct
OPTION 2
+ SPID for Vendor Expense
+ migration → end CY2026
OPTION 3
Full consolidation (migration incl.)
COMMITTED DEADLINE — SEP 26
Only Option 1 lands inside the committed window. Every scope addition (SPID, migration, remaining flows) moves delivery in month-sized steps — driven by schema transformation and discovery, not build effort.
USFF × EMS Consolidation — Delivery Options | Technology Delivery | July 2026
9

## Slide 10
TECHNOLOGY DELIVERY RECOMMENDATION
Ship Option 1 in September. Phase the rest.
Why Option 1
It is the only option that meets the committed date with high confidence — scope is already proven by working prototypes.
It contains the two biggest unknowns (data migration and SPID / Ariba) instead of betting the deadline on them.
Non-GTS users are untouched; GTS gets immediate consolidation value on the highest-volume flow.
The phased path
1
PHASE 1 · SEP 2026 Option 1 live — EMS triage + Pipeline for Vendor Expense in USFF
2
PHASE 2 · Q1 FY27 SPID for Vendor Expense + data migration + Ariba SR validation (Option 2 scope)
3
PHASE 3 · FY27 Remaining flows & decommission — sized only after real requirements exist (Option 3 scope)
What we need from leadership today
Endorse the scope
Approve Option 1 for the September window and Phase 2 (SPID + migration) for Q1 FY27 planning.
Unlock requirements
Direct the EMS / business team to hand over the expense policy, skills master, rate tables and PowerApps logic — our largest source of risk.
Sponsor the Ariba engagement
Kick off the Ariba API request now; it is the longest-lead item on the Phase 2 critical path.
Decide on capacity
Confirm developer backfill after August — the team drops to 2 developers while this programme runs.
USFF × EMS Consolidation — Delivery Options | July 2026 | Confidential
10