EMS INTEGRATION — EXECUTIVE TIMELINE SUMMARY

USFF × EMS/SPID Consolidation

July 10, 2026

Bottom line A real, working September pilot is achievable — one expense type, native in USFF, approvals still on today's process. Replacing today's approval process entirely is realistic Dec 2026–Feb 2027, depending on staffing. Committing to the full system by September is not realistic and risks the compliance/governance quality this program exists to deliver.

| Milestone | One team | + 2nd track |
| --- | --- | --- |
| September Pilot — 1 expense type live | Sep 20, 2026 | Sep 6, 2026 |
| All 5 expense types live (today's approval process) | Nov 15, 2026 | Oct 4, 2026 |
| Governed approvals live — today's process retired | Feb 21, 2027 | Dec 13, 2026 |
| Full program — + integrations + reporting | Apr 18, 2027 | Jan 10, 2027 |

## Why This Matters Beyond This Project

This program is on the critical path for other planned UI integrations and for the Gen AI model completion. That raises the cost of getting the date wrong in either direction: forcing an unrealistic September full-launch risks rework and compliance exposure that delays those dependent efforts even further, while the achievable pilot path above keeps them moving on the earliest honest date.

## Top Risks

- 3 business inputs still outstanding (expense-policy document, data-lake schema, GTS-detection decision) gate the 2027 rows — not an engineering constraint.

- “+2nd track” dates require staffing a second team now, not deciding to later.

- 6 external-team dependencies (Onboarding, Invoicing, GD Hub, etc.) aren't yet scheduled on their side.

- Dependent initiatives inherit any slip here — sequencing risk, not just this program's own risk.

## Recommendation

- Commit publicly to the September Pilot, not a full-system date.

- Unblock the 3 outstanding business inputs this month — highest-leverage action available to leadership.

- Decide now on staffing a second track if Dec 2026 (vs. Feb 2027) matters to dependent initiatives.