## Slide 1
USFF × EMS Integration
Recommendation: deliver the Vendor Expense flow end-to-end in September — phase the remaining flows behind documented requirements.
EMS Triage
→
Pipeline
→
USFF Intake
→
Ariba SR
→
SPID
→
DocuSign
Shipping in September (Phase 1) — already prototyped and demoed
EMS triage embedded in USFF — one front door for GTS; non-GTS users completely untouched
Pipeline intake + BOM agenda approvals — matrix-routed, every approval date-stamped for audit
Approved pipelines continue one click into our existing USFF / Ariba intake, pre-populated
SPID Vendor Expense — validates Pipeline + Ariba, asks only net-new questions, flags changes in red
The other four expense tiles redirect to today’s Signing Party PowerApp — zero disruption
Why Vendor Expense first?
It is the only EMS expense type that touches procurement, Ariba and the USFF storefront — the highest-value slice, and the one we can validate end-to-end today.
Supporting material: 60-second walkthrough video · clickable prototype · 34-screen pack · two-flow process map

## Slide 2
Why “everything by September” is not feasible
The team is aligned: the EMS triage and the Pipeline are not the risk — encapsulating the Signing Party (SPID) flows is.
1
No requirements exist
We are reverse-engineering the EMS and SPID PowerApps from scratch by using the live apps. Discovery is still changing the model — the last business call materially corrected the flow we had built to.
2
SPID is the hard part
Each expense type has its own SPID intake with distinct conditional logic and different data pulled in — 165+ business rules extracted so far, none yet validated by the business.
3
The data is not in our hands
11 sources still owed: the expense policy, skills master, rate-table repository, valid pipeline list, vendor SR repository, shared data-lake schema, and more.
4
Downstream coupling, no specs
SPID flows feed the onboarding portal + shared data lake, the GD Hub automated feed (mechanism unknown), a manual invoicing mailbox, and a Pre-Intake bot owned by another team.
5
Approval to Hire alone is a project
Five-way front-door branching, tenure-extension gating, bulk resource and rate logic, conditional AMCB sections, and vendor reuse rules.
6
These are financial controls
Shipping unvalidated approval logic risks broken audit evidence and mis-routed spend approvals — a worse outcome than a later, correct delivery.

## Slide 3
The phased path — and what we need
PHASE 1 — SEPTEMBER
Vendor Expense end-to-end: EMS triage, Pipeline + BOM agendas, USFF / Ariba intake, SPID Vendor Expense. Redirect model for everything else.
Prototype built — in business review
PHASE 2 — APPROVAL TO HIRE
ATH front-door branching, bulk resources, reuse rules and the ATH SPID.
Starts when the skills master + rate tables are delivered and ATH requirements are signed off
PHASE 3 — PROJECT · OTHER APPROVALS · INVOICES
Remaining SPID intakes plus downstream automation (non-Ariba invoice hand-off, onboarding feeds).
Starts when downstream specs (data lake, GD Hub, invoicing) are delivered and signed off
Phases are gated on signed-off requirements, data access and UAT with real users — not on calendar dates.
What we need from leadership
1
Endorse the phased scope
Hold September to Phase 1.
2
Unblock discovery
Direct the EMS team to deliver the 11 outstanding artifacts and name an SME per flow — our bottleneck is reverse-engineering, not build capacity.
3
Accept the redirect model
The other flows keep working exactly as today until their phase — no user impact.