## Onboarding Workback
GLOBALITY: AI-ENABLED SOURCING SOLUTION - VENDOR ONBOARDING WORKBACK
Status as of July 11, 2026 ¦ Contract Status: NOT YET SIGNED ¦ Prepared for onboarding alignment discussion
CRITICAL GAP: Business requirements, phased rollout scope, and RBAC/AD-group design are NOT yet locked down. These must be defined BEFORE SSO, architecture, and environment decisions can be finalized - see Section 0 below.
Item # (Workstream / Phase) | Task | Owning Team(s) | Vendor Support Required? | Specific Vendor Ask / Deliverable | When Can This Happen? (Relative to Contract Signing) | Start Date | Target Date | Duration (Days) | Status | Comments / Dependencies
0. FOUNDATIONAL PRE-REQUISITE - LOCK BUSINESS REQUIREMENTS & SCOPE (MUST BE DONE FIRST)
0.1 | Define business problem, rationale & target outcomes | Business | No |  | Foundational - blocks all scope-dependent work |  |  |  | Not Started | GAP: Not yet formally defined. Needed to justify solution and anchor all downstream artifacts.
0.2 | Define phased rollout plan (Phase 1 / 2 / 3) and which capabilities are mandatory vs. optional per phase | Business | No |  | Pre-Contract (Foundational - Do First) |  |  |  | Not Started | Business has stated a phased rollout but phases are undefined. This drives which Globality services are needed at each stage, the Architecture Blueprint, and the Control Gap Assessment scope.
0.3 | Confirm in-scope channels/interfaces (confirm no mobile app in scope) | Business | No |  | Pre-Contract (Foundational - Do First) |  |  |  | Not Started | A mobile app would trigger an additional governance artifact. Globality currently has no mobile app - but this must be explicitly confirmed and documented in scope, not assumed.
0.4 | Clarify what "SSO by end of fiscal (Oct 31)" means: pre-prod/test only, or full production | Business + Tech | No |  | Pre-Contract (Foundational - Do First) |  |  |  | Not Started | Prod deployment cannot occur without a Model/No-Objection approval, which can take up to 2 months. If "end of fiscal" means PROD, the timeline needs to be reset now, not discovered later.
0.5 | Confirm number of environments required (Globality reported to offer Pre-Prod & Prod only) | Tech / IAM Team | YES | Vendor to confirm standard environment/tenant offering (pre-prod, prod) and any sandbox options | Pre-Contract (Foundational - Do First) |  |  |  | Not Started | Environment count is not yet locked down - required before SSO app registrations or SCIM design can start.
0.6 | Define RBAC model and required Active Directory (AD) groups | Business + IAM Team | No |  | Pre-Contract (Foundational - Do First) |  |  |  | Not Started | Roles and access requirements have not been determined yet. This is a hard dependency for SSO/SCIM configuration (Section 7) - cannot be skipped to "just turn SSO on."
0.7 | Draft & finalize Business Requirements Document (BRD) | Business (Product Owner/SME) | No |  | Foundational - gates solutioning |  |  |  | Not Started | THE key artifact: this is how the solution gets architected, scoped, and staffed. Nothing in Sections 3-7 should be finalized before this is locked.
1. BUSINESS NEED & VENDOR ENGAGEMENT (Pre-Contract - Sourcing & Contracting)
1.1 | Identify business need, problem statement & rationale | Business | No |  | Pre-Contract (Sourcing & Contracting) |  |  |  | Not Started | Feeds the intake submission below.
1.2 | Submit Intake / Initiate Vendor Engagement (Ariba Sourcing Request) | Business + Project Manager | No |  | Pre-Contract (Sourcing & Contracting) |  |  |  | In Progress | Nadia has already started this. Requires: business justification, scope of service, vendor information, funding confirmation - scope/justification must be shared across workstreams.
1.3 | Negotiate Contract & MSA | Sourcing (SSG) + Legal | YES | Vendor commercial/legal contact for redlines and terms | Pre-Contract (Sourcing & Contracting) |  |  |  | Not Started | SSG leads commercial terms & legal T&Cs; facilitates risk-related schedules.
1.4 | Ensure NDA is signed | Sourcing (SSG) + Vendor | YES | Vendor signatory | Pre-Contract (Sourcing & Contracting) |  |  |  | Not Started
2. RISK INTAKE & THIRD-PARTY DOCUMENTATION (Pre-Contract - Risk & Architecture Review)
2.1 | Submit Inherent Risk Assessment (IRA) | Business + BISO | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started | Determines engagement risk tier and which downstream controls/assessments are required.
2.2 | Create MalCode | Tech Team | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
2.3 | Launch Third-Party Risk Assessments (TPSD / 3PCRM / security reviews) | Business / PM / BISO | YES | SOC 2, ISO 27001, vulnerability management reports, security whitepapers, architecture diagrams | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started | Runs throughout the Third-Party Management Lifecycle (TPML). Vendor docs can - and should - be requested now, before signature.
2.4 | Collect vendor privacy documentation | Business / BISO | YES | Data handling practices, data residency, retention & deletion policy | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
2.5 | Collect vendor operational documentation | Business / BISO | YES | Support model, escalation procedures, disaster recovery plan | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
2.6 | Collect vendor architecture & integration documentation | Solution Architect | YES | API specifications, SSO/SCIM/auth documentation, integration guide | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started | Required input for TARA, Architecture Blueprint, and SSO build.
2.7 | Collect vendor AI/model documentation | Tech / Model Risk | YES | Training data description, model security controls, AI governance documentation | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started | Feeds Model Risk Onboarding (Section 5).
3. SECURITY & ARCHITECTURE REVIEWS (Pre-Contract - Risk & Architecture Review, continued)
3.1 | Engage BISO | Business / PM | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
3.2 | Complete TARA (Technology Asset Risk Assessment) | Solution Architect / BISO | YES | Vendor input/documentation required to complete the assessment | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
3.3 | Complete Control Gap Assessment (CGA) | BISO / Solution Architect | YES | Vendor documentation describing how identified gaps are mitigated/circumvented | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
3.4 | Architecture Blueprint diagram & APAT approval | Solution Architect | YES | Vendor architecture & API documentation | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started | Directly dependent on the BRD and locked phased scope (Section 0) - mandatory vs. optional features determine what Globality must provide.
3.5 | Threat Model | Solution Architect | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
3.6 | Determine if TD infrastructure is required (confirm pure SaaS hosting) | Solution Architect / Infra | YES | Vendor confirmation of hosting model (fully SaaS vs. any TD-hosted component) | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started | If infra IS required: initiate a Project ticket + Demand ticket, and a PID document with the Infra Architect.
3.7 | SCALE CSP Assessment (Cloud/SaaS Governance) | Tech Team / SCALE | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
4. PRIVACY REVIEWS
4.1 | Privacy Impact Assessment (PIA) | Business | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
4.2 | Data Impact Assessment (DIA) | Business | No |  | Pre-Contract (Risk & Architecture Review) |  |  |  | Not Started
5. MODEL RISK ONBOARDING - AI COMPONENT (Pre-Contract - Model / AI Risk Review; can take up to 2 months for No-Objection)
5.1 | Confirm model scope, sponsor, owner, developers, in-scope regions & entities | Business | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started | Directly dependent on the BRD / locked phased scope.
5.2 | AI Security Intake | Tech Team | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.3 | Change Risk Assessment (CRA) | Tech Team | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started | Required as input to the No-Objection Memo.
5.4 | Model Registration (MRMGE) | Tech Team / BSA | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.5 | Model Risk Assessment (EMRA) | Tech / BSA / Model Risk Team | YES | Vendor AI/model documentation (from Section 2) | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.6 | Compliance Model Intake & Approval (COMO) | Compliance / Model Risk | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.7 | New Technology Assessment (NTA) | Tech Team | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.8 | AI Control Gap Assessment (AI-CGA) | BISO / Model Risk | YES | Vendor AI governance & control documentation | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.9 | Accessibility Testing | Tech Team / QA | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started
5.10 | Obtain No-Objection Memo | Model Risk / Compliance | No |  | Pre-Contract (Model / AI Risk Review) |  |  |  | Not Started | REQUIRED before ANY production deployment. Can take up to 2 months - this is the critical-path item for a production SSO/go-live date.
6. CONTRACT EXECUTION - FINAL GATE (Sourcing, Risk Review & Model Risk Review must all be complete)
6.1 | Obtain final approvals across Sourcing, Risk Gating & Model Risk tracks | PM / Sourcing / Legal | No |  | Pre-Contract (Final Gate Before Signature) |  |  |  | Not Started
6.2 | Contract signed & executed | Legal / Vendor Management | YES | Vendor signatory | Pre-Contract (Final Gate Before Signature) |  |  |  | Not Started | HARD GATE: no user/account provisioning into the application is permitted until the contract is signed.
7. TECHNICAL ONBOARDING - POST-CONTRACT (Business priority: SSO)
7.1 | Confirm environments (Pre-Prod & Prod) directly with vendor | Tech / IAM Team | YES | Vendor to confirm environment/tenant setup and access | Post-Contract |  |  |  | Not Started
7.2 | Review Azure Entra ID onboarding & register new application | IAM Team | No |  | Post-Contract |  |  |  | Not Started
7.3 | Configure SSO - Pre-Prod (Entra ID) | IAM Team + Vendor Engineer | YES | Vendor engineer to provide SSO documentation and redirect URLs, and join a working session | Post-Contract |  |  |  | Not Started | ★ BUSINESS PRIORITY. Hard dependency on RBAC/AD groups (Section 0) and confirmed environments - cannot start meaningfully before those are locked.
7.4 | SCIM provisioning setup (if onboarding AD groups) | IAM Team + Vendor Engineer | YES | Vendor SCIM/API documentation and implementation support | Post-Contract |  |  |  | Not Started
7.5 | Define application roles & entitlements (Access Management / AMH) | Business + IAM Team | No |  | Post-Contract |  |  |  | Not Started
8. TESTING & PRODUCTION READINESS
8.1 | Test SSO (Pre-Prod) | Tech Team + Vendor Support | YES | Vendor support analyst for troubleshooting/co-testing | Post-Contract |  |  |  | Not Started
8.2 | Security testing | Tech / Security Team | YES | Vendor security point of contact | Post-Contract |  |  |  | Not Started
8.3 | Firewall / DLP configuration (if required) | Tech / Infra | No |  | Post-Contract |  |  |  | Not Started
8.4 | Obtain testing sign-off | Business / Tech / PM | No |  | Post-Contract |  |  |  | Not Started
9. PRODUCTION DEPLOYMENT
9.1 | Configure SSO - Production | IAM Team + Vendor Engineer | YES | Vendor engineer support for production cutover | Post-Contract |  |  |  | Not Started | BLOCKED until the No-Objection Memo (Section 5) is obtained.
9.2 | Production deployment / application go-live | Vendor + Tech Team | YES | Vendor deployment/implementation support during cutover | Post-Contract |  |  |  | Not Started | Requires No-Objection Memo complete. If "end of fiscal" (Oct 31) means PROD, this is the realistic window - assuming No-Objection tracks on schedule.
10. CHANGE MANAGEMENT & DAY 2 SUPPORT
10.1 | Change management & communications | Business / Comms | No |  | Post-Contract |  |  |  | Not Started
10.2 | Day 2: ongoing vendor management & support | Vendor + Internal Support Team | YES | Vendor account manager and support analyst for ongoing SLA management | Ongoing (Post Go-Live) |  |  |  | Not Started

## Vendor Resources Needed
GLOBALITY VENDOR RESOURCES REQUIRED DURING ONBOARDING
Vendor Role | Purpose / What We Need From Them | Onboarding Phase(s) Needed
Account Manager / Commercial Lead | Owns commercial relationship, contract negotiation, and pricing enhancements. | Contracting (Pre-Contract - Sourcing)
Security / Compliance Point of Contact | Provides SOC 2, ISO 27001, vulnerability management reports, security whitepapers, and answers TARA/CGA questionnaires. | Third-Party Risk, Security & Architecture Reviews
Solutions/Implementation Engineer | Provides architecture & API documentation; supports SSO configuration incl. redirect URLs, SCIM setup, and integration testing. | Architecture Review, Technical Onboarding, Testing
AI/Model Governance SME | Provides training data descriptions, model security controls, and AI governance documentation for Model Risk Onboarding. | Model Risk Onboarding
Privacy/Data Protection Contact | Provides data handling, residency, and retention/deletion documentation for PIA/DIA. | Privacy Reviews
Implementation / Onboarding Project Manager | Coordinates vendor-side milestones and resourcing across parallel workstreams; single point of escalation. | All phases
Technical Support / Escalation Analyst | Provides day-to-day support during SSO/security testing and prod cutover troubleshooting. | Testing & Prod Readiness, Prod Deployment
Customer Success / Day 2 Support Contact | Owns ongoing SLA management, incident escalation, and account health post go-live. | Day 2 / Ongoing

## Legend & Open Questions
LEGEND & KEY OPEN QUESTIONS FOR THE BUSINESS
OWNING TEAM COLOR KEY
Business
Tech Team
PM / Sourcing / Legal
BISO / Risk / Compliance
IAM Team
Solution Architect
Model Risk
Compliance
Legal / Contracting
Vendor-Led Activity
VENDOR SUPPORT REQUIRED
Gold highlight = a Globality resource, documentation, or working session is required for that task.
STATUS COLOR KEY
Not Started
In Progress
Blocked
Done
ROSE/RED ROW TINT
Light red row tint = flagged risk, hard dependency, or hard gate - read the Comments column.
OPEN QUESTIONS THE BUSINESS STILL NEEDS TO ANSWER
# | Question | Why It Matters | Impacts
1 | What are the phase 1 / 2 / 3 MVP requirements, and which features are mandatory vs. optional? | Drives which Globality modules/services are needed, when, and shapes the Architecture Blueprint and CGA scope. | Architecture Blueprint, CGA, Vendor Scoping
2 | Does "SSO by end of fiscal" mean pre-prod/test, or full production? | Prod deployment requires a No-Objection Memo that can take up to 2 months - the target date must reflect that. | SSO Timeline, Model Risk Track
3 | How many environments do we actually need (pre-prod / prod only, or additional)? | Vendor is believed to offer only pre-prod and prod - needs explicit confirmation before SSO app registration begins. | IAM App Registration, SSO Design
4 | What roles/RBAC and AD groups are required for this application? | Not yet defined. SSO/SCIM cannot be meaningfully configured without this. | SSO, SCIM, Access Management
5 | Is the application fully SaaS, or is any TD-hosted infrastructure involved? | Determines whether a Project/Demand ticket and Infra Architect PID are required. | Infrastructure, Architecture Blueprint
6 | Is a mobile experience in scope, now or in a later phase? | Mobile would trigger an additional governance artifact not currently planned for. | Governance Scope, CGA
7 | Has funding been confirmed for this engagement? | Required as part of the intake submission; unresolved funding can stall Track A. | Vendor Intake / Sourcing
8 | What data will flow to/from Globality, and are there data residency constraints? | Needed for PIA/DIA and vendor privacy documentation review. | Privacy Reviews (PIA/DIA)
9 | Who is the accountable Business Owner/Sponsor for the AI model component? | Required for Model Risk Onboarding intake (scope, sponsor, owner, entities). | Model Risk Onboarding
10 | What is the realistic go-live date for PRODUCTION, accounting for the ~2-month No-Objection Memo timeline? | Business is targeting end of fiscal (Oct 31); if that's meant for prod, the workback above already assumes an aggressive but achievable path - any slippage in Model Risk pushes this out. | Overall Timeline