TIMELINE FEASIBILITY — CAN THIS SHIP BY SEPTEMBER?

USFF × EMS/SPID Consolidation

Prepared July 10, 2026 · for leadership discussion

Bottom line Yes — if we deliberately narrow the first release. Cutting to one expense type (e.g., Approval to Hire) and deferring the new governed-approval engine — GTS keeps using today's approval process a bit longer — gets a real, working pilot live by September. All five expense types live by October–November. The full governed-approval system (replacing today's process entirely) lands December 2026–February 2027 depending on staffing. Trying to ship everything at once is what pushes this into 2027.

# The Lever: Scope, Not Speed

AI-assisted development speeds up writing code. It doesn't shrink the two things that actually gate this timeline: how much scope ships at once, and what still has to be validated with real approvers before go-live. The path to September isn't faster typing — it's sequencing the work so a narrow, real slice ships early and everything else follows.

- The Financial Approval Matrix and governed approval chains aren't needed to let GTS users submit requests — only to route approvals through the new system instead of today's process. Deferring that piece, and shipping one form type first, is what makes September possible.

- Three inputs are still outstanding from the business — the full expense-policy document, the data-lake schema, and the GTS-detection decision. These gate the governed-approval and integration phases specifically, not the September pilot.

- This system will eventually govern real financial approvals for a bank. Once the new approval engine goes live, every chain needs sign-off from real approvers against real data — that review cycle takes calendar time no matter how fast the code was written.

# Realistic Delivery Options

| Milestone | What ships | Not yet included | One team | + 2nd track |
| --- | --- | --- | --- | --- |
| September Pilot | GTS users submit one expense type (e.g., ATH) natively in USFF. | Other 4 expense types; approvals still run on today's process; reference data hand-loaded, not full admin tooling. | Sep 20, 2026 | Sep 6, 2026 |
| All forms live | All 5 expense types + both Pipeline types submittable natively. | Approvals still run on today's process. | Nov 15, 2026 | Oct 4, 2026 |
| Governed approvals live | Approval Matrix, agenda-based approval chains, Management Consulting workflow — today's process retired. | Downstream integrations, reporting. | Feb 21, 2027 | Dec 13, 2026 |
| Full program | + Onboarding/Invoicing/GD Hub integration + reporting. | — | Apr 18, 2027 | Jan 10, 2027 |

“+2nd track” assumes a second, fully-staffed workstream is productive starting now — not yet true. Treat that column as best-case, not committed. Which single expense type ships first (ATH vs. Vendor Expense vs. another) is a business-priority call, not an engineering one — costs are similar either way.

# Top Risks to Any Date Above

- Deferring the Approval Matrix past September only works if no September-pilot form secretly needs it — confirm with engineering before committing to this sequencing.

- The 3 outstanding business inputs (policy document, data-lake spec, GTS-detection decision) still gate the “Governed approvals” and “Full program” rows — not an engineering problem, but a scheduling one if they slip further.

- 6 external-team dependencies (Onboarding, Invoicing, GD Hub, etc.) aren't yet scheduled on their side.

- The “+2nd track” dates require staffing a second team now, not deciding to later.

- Running two approval processes side-by-side (legacy + USFF-native forms) between September and “Governed approvals live” needs an explicit interim-process decision from the business — not just an engineering task.

# Recommendation

- Commit to the September Pilot as the concrete, demoable milestone — it's real and achievable, unlike a full-program September date.

- Get a business decision now on which single expense type ships first, and how approvals work for it in the interim.

- Ask leadership to help unblock the 3 outstanding business inputs this month — that has more schedule impact on the 2027 rows than adding engineers does.

- If a second track is realistic, staff it now — it's what brings “Governed approvals live” from February into December.